## Sheet1
EXTRA ITEM STATEMENT No -I
Name Of Work: Construction of 1000 seat Hi-tech Auditorium at NIT Hazratbal Srinagar (J&K) . SH - Building Work expect Acoustic ,false ceiling of Auditorium , chairs , carpets , Curtain , Kitchen Equipments , furniture etc.
Name of Contractor : - M/s Abdul Salam Mir Construction Co Pvt Ltd. |  | S. No. | E.I Sanctioned by A.E | E.I Sanctioned by E.E | E.I Sanctioned by S.E | Remarks
Agreement No. : - 09/EE/SPD/2018-19 |  | 1 |  |  | 2,95,32,360 | 13.24%
Tender Amount : 22,30,33,051 | [6 empty] | 29532360 | 13.2412
Date of Start :- 12.12.2018 |  | Total |  |  | 2,95,32,360 | 13.24% | 29532360 | 13.2412
Date of Completion :- Work in Progress. |  | Power | 1,80,000/- | 30,00,000/- | 5,00,00,000/-
Sr. No | Item | Qty |  | Rate | Amount | Remarks
1 | Wiring for light point / fan point/ exhaust fan point/ call bell point with 1.5 sq.mm FRLS PVC insulated copper conductor single core cable in surface/ recessed steel conduit, with modular switch, modular plate, suitable GI box and earthing the point with 1.5 sq. mm. FRLS PVC insulated copper conductor single core cable etc. as required. |  |  |  |  | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. |  |  | 0.07
a | Group C ( DSR 1.3.3 ) | 380 | points | 1824 | 693120
2 | Wiring for group controlled (looped) light point / fan point/exhaust fan point/ call bell point (without independent switch with 1.5 sq.mm FRLS PVC insulated copper conductor single core cable in surface / recessed steel conduit, 2 way modular switch , modular plate, suitable GI box and earthing the point with 1.5 sq.mm FRLS PVC insulated copper conductor single core cable etc. as required. | [6 empty] | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup
a | Group C ( DSR 1.54.3) ) | 87 | points | 1082 | 94134
3 | Wiring for circuit/ submain wiring alongwith earth wire with the following sizes of FRLS PVC insulated copper conductor, single core cable in surface/ recessed steel conduit as required.
a) | 2 X 1.5 sq. mm + 1 X 1.5 sq. mm earth wire (DSR 1.7.1) | 1000 | Mtrs | 323 | 323000
b) | 2 X 6 sq.mm + 1 X 6 sq.mm earth wire (DSR 1.7.4) | 300 | Mtrs | 582 | 174600
c) | 4 X 6 sq. mm + 2 X 6 sq. mm earth wire (for light DB) (DSR 1.7.9) | 300 | Mtrs | 914 | 274200
d) | 4 X 10 sq. mm + 2 X 6 sq. mm earth wire (for Power DB) (DSR 1.7.10) | 300 | Mtrs | 1153 | 345900
4 | Wiring for light/ power plug with 2X4 sq. mm FRLS PVC insulated copper conductor single core cable in surface/ recessed steel conduit alongwith 1 No. 4 sq. mm FRLS PVC insulated copper conductor single core cable for loop earthing as required. (DSR 1.5) | 650 | Mtrs | 428 | 278200
5 | Wiring for light/ power plug with 4X4 sq. mm FRLS PVC insulated copper conductor single core cable in surface/ recessed steel conduit alongwith 2 Nos. 4 sq. mm FRLS PVC insulated copper conductor single core cable for loop earthing as required. (DSR 1.6) | 300 | Mtrs | 655 | 196500
6 | S/F of following sizes of steel conduit along with the accessories in surface/ recessed i/c painting in case of surface conduit or cutting the wall & making good the same in case of recessed conduit etc as required.
a) | 20mm ( For Telephone) (DSR 1.20.1) | 200 | Mtrs | 221 | 44200
b) | 25mm (DSR 1.20.2) | 200 | Mtrs | 253 | 50600
c) | 32mm (DSR 1.20.3) | 100 | Mtrs | 322 | 32200
d) | 40mm (DSR 1.20.4) | 30 | Mtrs | 465 | 13950
7 | S/F of following sizes of PVC conduit along with the accessories in surface/ recessed i/c cutting the wall & making good the same in case of recessed conduit etc as required. (For Data cable) |  |  |  |  | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup.
a) | 25mm (DSR 1.21.2) | 400 | Mtrs | 143 | 57200
b) | 32mm (DSR 1.21.3) | 150 | Mtrs | 182 | 27300
8 | Supplying and fixing modular blanking plate on the existing modular plate & switch box excluding modular plate as required. (DSR 1.26) | 20 | Nos | 40 | 800
9 | Supplying and drawing co-axial TV cable RG-6 grade, 0.7 mm solid copper conductor PE insulated, shielded with fine tinned copper braid and protected with PVC shealth in the existing surface/ recessed steel /PVC conduit as required. (Make: ISI marked) (DSR 1.19) | 100 | Mtrs | 46 | 4600
10 | Supplying and drawing following pair 0.5 mm dia FRLS PVC insulated annealed copper conductor, unarmored telephone cable in the existing surface/ recessed steel/ PVC conduit as required.(Make: ISI marked)
a) | 2 Pair (DSR 1.18.2) | 350 | Mtrs | 38 | 13300
11 | Supplying and fixing following modular type switch /socket on the existing modular plate & switch box including connections but excluding modular plate etc. as required.
a) | RJ 45 Socket out let | 24 | Nos. | 967 | 23208 |  | M/R
b) | TV antenna socket outlet (DSR 1.24.7) | 5 | Nos. | 146 | 730
c) | Telephone socket outlet (DSR 1.24.6) | 10 | Nos. | 146 | 1460
12 | Supplying and fixing two module stepped type electronic fan regulator on the existing modular plate switch box including connections but excluding modular plate etc. as required. (DSR 1.25) | 32 | Nos. | 365 | 11680
13 | Supplying and fixing following sizes/ module, GI box along with modular base & cover plate for modular switches in recess etc complete as required.
a) | (1 or 2 Module) 75 mm x 75 mm (DSR 1.27.1) | 46 | Nos. | 295 | 13570
14 | Supplying and fixing suitable size GI box with modular plate and cover in front on surface or in recess, including providing and fixing 3 pin 5/6 amps modular socket out let and 5/6 amps modular switch, connection, painting etc as required. (DSR 1.31) | 45 | Nos. | 472 | 21240
15 | Supplying and fixing suitable size GI box with modular plate and cover in front on surface or in recess, including providing and fixing 6 pin 5 & 15/16 amps modular socket out let and 15/16 amps modular switch, connection, painting, etc as required. . (DSR 1.32) | 109 | Nos. | 579 | 63111
16 | Supplying and fixing suitable size GI box with modular plate and cover in front on surface or in recess including providing and fixing 1 x 15/16 amps modular switch and 3 Nos x 3 pin 5/6 amps socket Outlet, connection earthing, painting etc complete as required.. | 30 | Nos. | 976 | 29280 |  | MR
17 | Supplying & fixing suitable size GI box with modular plate and cover in front on surface or inrecess including providing and fixing 25 A modular socket outlet and 25 A modular SP MCB,“C” curve including connections, painting etc. as required. (For Geyser Point) (DSR 1.57) | 24 | Nos. | 719 | 17256
18 | Providing laying, testing & commissioning of 'C' class heavy duty MS Pipe conforming to IS 1239/3589 i/c fittings like elbows, tees, flanges, tapers, nuts bolts, gaskets etc. in ground including welding, excavation & providing cement concrete blocks as supports, anticorrosive treatment with coaltar/asphalt tape as per IS 10221, refilling the trench etc. of following sizes complete as required. |  |  |  |  | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup.
b | 150 mm. Dia (DSR 18.6.2) | 300 | Mtrs. | 3762 | 1128600
19 | Providing, laying, testing & commissioning of 'C' class heavy duty MS pipe conforming to IS 3589/IS 1239 including Welding, fittings like elbows, tees, flanges, tapers, nuts bolts, gaskets etc. and fixing the pipe on the wall/ceiling with suitable clamp/support frame and painting with two or more coats of synthetic enamel paint of required shade complete as required :
a | 80 mm dia (DSR 18.7.6) | 42 | Mtrs. | 1864 | 78288
b | 100 mm dia (DSR 18.7.7) | 30 | Mtrs. | 2527 | 75810
c | 150 mm dia (DSR 18.7.8) | 75 | Mtrs. | 3534 | 265050
20 | Supplying, fixing, testing & commissioning of double flanged sluice valve of rating PN 1.6 with non rising spindle, bronze/gun metal seat, ISI marked complete with nuts, bolts, washers, gaskets and conforming to IS 780 of following sizes as required :
a | 200 mm dia (DSR 18.12.7) | 4 | Nos | 38894 | 155576
b | 150 mm dia (DSR 18.12.6) | 2 | Nos | 22509 | 45018
c | 80 mm (DSR 18.12.4) | 1 | No | 10577 | 10577
21 | Providing, installation, testing and commissioning of non-return valve of following sizes confirming to IS: 5312 complete with rubber gasket, GI bolts, nuts, washers etc.as required :
a) | 150 mm dia | 2 | nos. | 17588 | 35176
b) | 80 mm dia | 1 | nos. | 7605 | 7605
22 | Supplying and fixing single headed internal hydrant valve with instantaneous Gunmetal/Stainless Steel coupling of 63 mm dia with cast iron wheel ISI marked conforming to IS 5290 (Type -A) with blank Gunmetal/Stainless Steel cap and chain as required :
a | Single headed Gunmetal (DSR 18.9.1) | 8 | Set | 7561 | 60488
23 | Supplying and fixing Single headed external yard hydrant valve with 1 No. 63 mm dia instantaneous FM Gunmetal/ Stainless Steel coupling and cast iron wheel,ISI marked, conforming to IS 5290 (type A) with blank Gunmetal/Stainless Steel cap and chain as required :
a | Single headed Gunmetal (DSR 18.10.1) | 7 | Set | 7561 | 52927
24 | Supplying, fixing, testing and commissioning of butterfly valve of PN 1.6 rating with bronze/gunmetal seat duly ISI marked complete with nuts, bolts, washers, gaskets conforming to IS 13095 of following sizes as required :
a | 80 mm dia (DSR 18.11.4) | 7 | Set | 4927 | 34489
b | 100 mm dia (DSR 18.11.5) | 2 | Set | 6593 | 13186
c | 150 mm dia (DSR 18.11.6) | 2 | Set | 8860 | 17720
25 | Supplying and fixing orifice plate made out of 6 mm thick stainless steel (Grade 304) with orifice of required size to be fitted between flange & landing valve of external and internal hydrants to reduce pressure at the outlet to the level of 3.5 kg/cm 2 complete as required. ( DSR 18.13 ) | 15 | Nos. | 1306 | 19590 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup.
26 | Supplying and fixing of fire brigade connection of cast iron body with gun metal male instantaneous inlet couplings complete with cap and chain as reqd. for suitable dia MS pipe connection conforming to IS 904 as required :
a | 3 way-150 mm dia M.S. Pipe ( DSR 18.19.3 ) | 2 | Set | 9350 | 18700
27 | Providing, fixing, testing & commissioning of installation control valve of cast iron body, brass / bronze working parts comprising of water motor alarm, bronze seat clapper, clapper arm and hydraulically driven mechanical gong bell to sound continuous alarm when the wet riser/sprinkler system activates, pressure gauges, emergency releases, strainer, pressure switch, cock valve complete with drain valve and bypass, test control box, ball valves, MS pipe of required size, flanges, orifice plate, gasket etc of follwing sizes as required :
a | 100mm dia ( DSR 18.24.2 ) | 1 | Sets | 44501 | 44501
28 | Supplying & fixing 63 mm dia gun metal short branch pipe with 20 mm nominal internal diameter size nozzle conforming to IS 903 suitable for instantaneous connection to interconnect hose pipe coupling as required :
a | Gun metal ( DSR 18.18.1 ) | 17 | Nos. | 2389 | 40613
29 | Providing & fixing weather proof standard hose cabinet ( 900 mm x 600 mm x 500 mm ) outdoor type, suitable for accommodating yard hydrants, made out of 2 mm thick MS sheet having glazed door with 6 mm thick clear glass including necessary locking arrangement suitable to accomodate external hydrant with butter fly valve powder coating with Post Office Red paint and for housing 2 Nos. 15 mtrs RRL hose pipe, 1 No. branch pipe including grouting on a PCC foundation or on wall as per site requirement and suitable inscripting the words "Hose Cabinet" on the Box complete as required. ( For yard hydrant) | 7 | Nos. | 16389 | 114723 |  | M.R
30 | Providing and fixing standard fireman's axe with heavy insulated rubber handle conforming to IS: 926 complete. | 26 | Nos. | 934 | 24284 |  | MR
31 | Supply, installation, testing & commissioning of Gun Metal Fire brigade suction hose coupling (Draw-out Connection) with nut for female coupling as per IS:902-1974 complete with 100 mm dia. GI suction pipe and 100 mm dia. 1 No. CI foot valve flanged (to be connected to static water tank). | 1 | Nos. | 13611 | 13611 |  | N.S
32 | Providing and fixing in position the industrial type pressure gauges 100 mm dia with gun metal / brass valves with Siphone pipe 3/8"(S/S) complete as required. ( DSR 16.8 ) | 4 | nos. | 1183 | 4732
33 | Providing, installation, testing and commissioning of stainless steel Y-strainer fabricated out of 1.6 mm thick stainless steel, Grade 304, sheet with 3 mm dia holes with stainless steel flange.
a) | 150mm dia ( DSR 18.15.3 ) | 2 | Nos | 11020 | 22040
34 | Supplying & laying of 2x1.5 sqmm fire survival armoured cable, 600/1000V rated with annealed copper conductor having glass mica fire barrier tape covered by an extruded layer of Cross Linkable Ethylene Propylene Rubber (EPR) insulation and LSZH inner bedding, steel wire armouring & LSZH outer sheath complete as required. |  |  |  |  | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup.
a) | 2 x 1.5 sq.mm ( DSR 17.5.1 ) | 4000 | Metre | 355 | 1420000
PUBLIC ADDRESS SYSTEM
35 | Supplying and drawing of cable Fire Retardant PVC insulated copper conductor cable in the existing surface / recessed steel conduit of following pairs, cores and size including connections and interconnections etc. as required.
a) | Speaker cable Single pair, 2-core, 1.5 sqmm (DSR 17.5.3.1) | 500 | Mtrs | 53 | 26500
36 | Supplying and fixing 25 mm dia MS flexible pipe with PVC coating along with all ancillaries and accessories like coupler etc. as required. (DSR 17.5.4) | 300 | Mtrs | 52 | 15600
37 | S/F of following sizes of steel conduit along with the accessories in surface/ recessed i/c painting in case of surface conduit or cutting the wall & making good the same in case of recessed conduit etc as required.
a) | 25mm ( DSR 1.20.2 ) | 500 | Mtrs | 253 | 126500
(Networking )
38 | Providing and fixing of lockable 12U wall /Floor Mounted Rack with Cable Manager for distribution, mounting of patch panels hubs, switches etc complete as required. | 1 | Nos | 8368 | 8368 |  | M/R
39 | Providing termination and fixing of CAT 6 termination patch panel of 24 ports, each for termination of CAT 6 cable including crimping, testing and certifying the network with omniscanner etc complete as required. | 1 | Nos | 6298 | 6298 |  | M/R
40 | Supplying and drawing of UTP 4 pair CAT 6 LAN Cable in the existing surface/ recessed Steel/ PVC conduit as required.
a) | 1 run of cable ( DSR 1.53.1 ) | 300 | mtrs | 56 | 16800
HVAC System
41 | Supplying, installation, testing and conmmissioning of refrigerant T/Y-Joint fittings and headers to all indoor units at all floors includng alingment of joints complete as required. | 45 | Nos. | 8654 | 389430 |  | MR
42 | Supply, Installation, testing and commissioning including vaccumization and Nitrogen testing of following nominal sizes of soft/hard drawn copper refrigerant piping for VRV/VRF system, complete with fittings, with suitable adjustable ring type hanger supports, jointing/brazing including accessories, insulated with XPLE Class-O tubular insulation/with Class-O closed cell elastometric nitrile rubber tubular sleeves sections of specified thickness as given below for Suction and Liquid lines, all accessories as per specifications etc. as required : ( VRV DSR Item No 5 )
a | a) 41.27 mm dia (OD) (Hard drawn) with tube thickness 1.62 mm with 19 mm thick insulation | 300 | Mtrs | 1294 | 388200 |  | 5.12
b | b) 38.1 mm dia (OD) (Hard drawn) with tube thickness 1.62 mm with 19 mm thick insulation | 25 | Mtrs | 1251 | 31275 |  | 5.11
c | c) 34.9 mm dia (OD) (Hard drawn) with tube thickness 1.62 mm with 19 mm thick insulation | 20 | Mtrs | 1216 | 24320 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | 5.1
d | d) 31.8 mm dia (OD) (Hard drawn) with tube thickness 1.62 mm with 19 mm thick insulation | 20 | Mtrs | 1157 | 23140 |  | 5.9
e | e) 28.58 mm dia (OD) (Hard drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 110 | Mtrs | 1096 | 120560 |  | 5.8
f | f) 25.4 mm dia (OD) (Hard drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 25 | Mtrs | 1011 | 25275 |  | 5.7
g | g) 22.2 mm dia (OD) (Hard drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 150 | Mtrs | 855 | 128250 |  | 5.6
h | h) 19 mm dia (OD) (Hard drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 650 | Mtrs | 699 | 454350 |  | 5.5
i | i) 15.86 mm dia (OD) (Soft drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 125 | Mtrs | 581 | 72625 |  | 5.4
j | j) 12.7 mm dia (OD) (Soft drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 90 | Mtrs | 461 | 41490 |  | 5.3
k | k) 9.5 mm dia (OD) (Soft drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 350 | Mtrs | 327 | 114450 |  | 5.2
l | l) 6.4 mm dia (OD) (Soft drawn) with tube thickness 1.2 mm with 19 mm thick insulation | 50 | Mtrs | 242 | 12100 |  | 5.1
Note: 1. The copper piping and piping circuit should be with minimum number of joints, which shall be attained by:
i) Using one end Expanded tubes. Ii) Bending the tubes instead of using elbow joints whereever 90 degree bending is required.
2) Piping should be routed at site in such a manner that brazed joints in refrigeration piping are kept to a minimum.
3) The makes of tube fittings shall be same as that of tubes.
4) The thickness of fittings used shall be same as that of pipe.
Condensate Drain Piping:
43 | Providing and fixing UPVC 6kg/Cm2 pipes of various sizes with 6 mm Nitrile insulation for condensed water drainage from Indoor unit to nearest disposal point in toilet/ outside rain water harvesting system as approved by architect/consultant
a) | 50 MM Dia | 80 | Rmt | 477 | 38160 |  | MR
b) | 32 MM Dia | 150 | Rmt | 405 | 60750 |  | MR
c) | 25 MM Dia | 350 | Rmt | 328 | 114800 |  | MR
Duct Works
44 | Supply, installation, balancing and commissioning of fabricated at site GSS sheet metal rectangular/round ducting complete with neoprene rubber gaskets, elbows, splitter dampers, vanes, hangers, supports etc. as per approved drawings and specifications of following sheet thickness complete as required
a) | Thickness 0.63 mm sheet ( DSR 16.12.2.1) | 300 | Sqm. | 1046 | 313800
b) | Thickness 0.80 mm sheet ( DSR 16.12.2.2) | 120 | Sqm. | 1215 | 145800
c) | Thickness 1.0 mm sheet ( DSR 16.12.2.3) | 60 | Sqm. | 1611 | 96660
45 | Supplying and fixing of following thickness duly laminated aluminum foil of mat finish closed cell Nitrile rubber (Class “O”) insulation on existing duct after applying suitable adhesive for Nitrile rubber. The joints shall be sealed with 50 mm wide and 3 mm thick self adhesive nitrile rubber tape insulation complete as per specifications and as required. |  |  |  |  | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup.
a) | 19 mm ( DSR 16.23.1) | 265 | Sqmt | 746 | 197690
b) | 25 mm ( DSR 16.23.2) | 265 | Sqmt | 957 | 253605
46 | Supply and fixing of acoustic lining of supply air duct and plenum with 25 mm thick resin bonded glass wool having density of 32 kg/m³, with 25 mm X 25 mm GI section of 1.25 mm thick, at 600 mm centre to centre covered with Reinforced Plastic tissue paper and 0.5 mm thick perforated aluminum sheet fixed to inside surface of ducts with cadmium plated nuts, bolts, stick pins, CPRX compound etc. complete as required and as per specifications. ( DSR 16.21) | 100 | Sqm. | 700 | 70000
47 | Supply, installation, testing and commissioning of GI volume control duct damper complete with neoprene rubber gaskets, nuts, bolts, screws linkages, flanges etc., as per specifications. ( DSR 16.13 ) | 15 | Sqm. | 6968 | 104520
48 | Supplying & fixing of powder coated extruded aluminium Supply Air Grills with aluminium volume control dampers.as per specifications. ( DSR 16.15 ) | 20 | Sqm. | 9004 | 180080
49 | Supplying & fixing of powder coated extruded aluminium Return Air Grills with louvers but without volume control dampers complete as required. ( DSR 16.16 ) | 20 | Sqmt | 5844 | 116880
50 | Supplying, fixing testing commissioning of supply air Jet Nozzles of powder coated aluminum with aluminum volume control dampers as per specification and Shop Drawings. | 30 | Nos | 7404 | 222120 |  | MR
51 | Supplying, fixing testing commissioning of supply air diffusers of powder coated aluminium with aluminium volume control dampers with anti smudge ring & removable core. ( DSR 16.17 ) | 15 | Sqmt | 12048 | 180720
52 | Supplying, fixing testing commissioning of Return air diffusers of powder coated aluminium without volume control dampers with anti smudge ring & removable core. ( DSR 16.18 ) | 15 | Sqmt | 8031 | 120465
53 | Supply & Installation of extruded aluminum volume control damper with blades, adjustable lever, frame etc for Supply Air and Fresh Air Connected to AHU as per specifications and drawings as complete as required. | 4 | Sqmt | 11522 | 46088 |  | MR
54 | Supply,Installation,Testing and commissioning of double layer canvas connection with 1/2 hr. fire rating as per specification. | 5 | Nos | 11057 | 55285 |  | MR
55 | Supplying, Fixing,testing and commissioning of fire damper in supply air duct/main branch and return air path as and where required of required sizes i/c control wiring, the damper shall be motorized and spring return so as to close the damper in the event of power failure automatically and open the same in case of power being restored. The spring return action shall be inbuilt mEChanism and not externally mounted. the damper shall also be closed in the event of fire signal complete as required adn as per specifications.
a | Fire damper ( DSR 16.20.1 ) | 4 | Sqm | 10540 | 42160 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup.
b | Actuator ( DSR 16.20.2 ) | 3 | Nos | 9837 | 29511
Video System
56 | Supply , Installation , Testing & Commissioning of Projection System with 16000 Lumens, Laser Phosphorus Projector, with WUXGA Resolution, 85% Center to Corner Uniformity, Inputs SDI In x 1, HDMI x 1 , DVI x 1, VGA x1 , RJ45 x 1, Control Ports RS232 IN / Out, Digital Link (HD Base-T) x 1, USB x 1, Remote IN / Out, Operating Temperature 0-45 C (32-113F). Lamp life 20,000 Hours, 360 degree projection installations, Logo transfer software, Portrait Installations, Geometric correction auto screen adjustment software compatible and Motorized zoom lens and complete as per the specifications. | 1 | No. | 3520965 | 3520965 |  | MR
57 | Supply , Installation , Testing & Commissioning of Motorized Projection Screen with Matt White fabric of size 4267mm (H) x 7315 mm (W), 1.5 Gain, Black boarder on both side, Wired / Wireless remote control and complete as per the specifications. | 1 | No. | 414231 | 414231 |  | MR
58 | Supply, Installation, Testing & Commessioning of HDBaseT transmitter for HDMI and USB-C with USB Hub, Input Port: 1 x HDMI, 1 x USB-C, Output Port: 1 x HDBaseT, Data Port: 1 x USB Host, 1 x USB HUB, Signal & Control Extension: Tranmitter for AV, Power, Control & Data upto 100mtr using CATx cable, Resolution Support: 4K 60 4:4:4, Remotely powered over HDBaseT, Auto Switching: Select Active input via Hot Plug & Video Detect Technology Auto Display Control: Automatic Display On / Off control based on switcher. Control signals to display are transmitted via IP, RS-232 or CEC.,Chroma Subsampling: 4:4:4, 4:2:2, 4:2:0, Color Depth: 8-bit, 10-bit, 12-bit"Audio Support: HDMI IN / HDBaseT OUT : Dolby Digital Plus, Dolby TrueHD, DTS-HD Master Audio, Bandwidth 10 Gbps, HDCP & EDID Management, Control : TCP/IP and RS-232, Cable Link Monitoring: Integrated HDBaseT link status monitoring | 1 | No. | 266291 | 266291 |  | MR
59 | Supply, Installation, Testing & Commessioning of HDBaseT receiver for HDMI with USB System Type: HDBaseT Receiver for HDMI with USB,Input Port: 1 x HDBT, Output Port: 1 x HDMI, Data Port: 2 x USB Hub or more, Signal & Control Extension: Receiver for HDMI, Ethernet, power, control, and USB upto 100mtr using CATxx cable Resolution Support: 4K 60 4:4:4"USB : Signal - 2.0 or better Maximum Data Rate - 480Mbps, Remote powering over HDBaseT or local powering,Chroma Subsampling: 4:4:4,Color Depth: 8-bit, 10-bit, 12-bit, "Audio Support: Pass-through: Dolby Digital Plus, Dolby TrueHD, DTS-HD, Master Audio, DTS:X, HDCP 2.2 & CEC Pass-through Cable Link Monitoring: Integrated HDBaseT link status monitoring | 1 | No | 266291 | 266291 |  | MR
60 | Supply, Installation, Testing & Commessioning of 5x2 Universal switcher with built-in / external Wireless Presentation Capable for Soft VC Facility 5 x 2 Multiformat Universal Matrix Switcher with built-in / External Wireless Facility Input Ports: 2 x HDMI, 1 x USB-C, 1 x Mini Display Port Output Ports: Matrix Video Output on HDMI, HDBT 4K 60 4:4:4 ,Automatic input selection using hot plug detect and video detection technology, EDID Management, HDCP Management (HDCP 2.2 Compliant), CEC Enable, Multi Channel Audio Compliant PCM, Dolby Digital, DTS Digital Surround etc Integrated HDBaseT link status monitoring, Soft VC Ready module with USB Host and USB Hub Ports, USB 2.0 interfacing and extension over HDBaseT,Selectable 4K60 4:4:4 video scaler downscaling Built-in / External Wi-Fi connectivity for an iOS, Android, Mac, Chromebook, or Windows-based device.Shall support Miracast /Chromecast/Air play., Built-in Audio de-embedding, HDBase T Outputs Extends HDMI, Power and Control over a single CAT6a OR CAT7 cable HDMI and HDBT output which can work as mirror mode or individual mode like matrix.HDCP 2.2 and EDID management | 1 | No. | 443819 | 443819 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
61 | Supply, Installation, Testing & Commessioning of 4 x 4 HDMI Matrix Switcher Input Port: 4 x HDMI, Output Port: 4 x HDMI, Resolution Support : 4K 60 4:4:4 ,Support HDR10 and Dolby® Vision™ @ 60Hz Manual Control: Front Panel Input Selection, LED Indicator: To provide power and input selection status information, Chroma Subsampling: 4:4:4, 4:2:2, 4:2:0, Color Depth 8-bit, 10-bit, 12-bit Audio Support:HDMI IN/Out: DTS 5.1, Dolby Digital+, Dolby TrueHD, DTS-HD Master Audio, Signal Bandwidth: 18 Gbps, HDCP 2.2 compliant, HDCP Management, EDID Management Additional Feature: Independent CEC display control to each output Control: TCP/IP, Configuration: GUI-based configuration using integrated web server HDMI audio extractor and downmix 2channel. | 1 | No. | 384643 | 384643 |  | MR
62 | Supply, Installation, Testing & Commessioning of 4K/UHD HDMI Extender Kit with Control and Remote Power : Supports resolutions up to 4K/UHD 60 Hz 4:2:0 System Type: 4K/UHD HDMI Extender Kit with Control and Remote Power Transmitter : Input Port: 1 x HDMI & Output Port : 1 x HDBT Receiver : Input Port: 1 x HDBaseT & Output Port : 1 x HDMI Signal & Control Extension: Tranmitter for AV, Power & Control upto 70mtr using CAT6a/7 cable Resolution Support: 4K/UHD @ 60 Hz with 4:2:0" Remote power, transmitter powers receiver over HDBaseT LED Indicator: To provide power and link status information HDBaseT link test verifies cable, termination, and link qualityChroma Subsampling: 4:4:4, 4:2:2, 4:2:0 Color Depth: 8-bit, 10-bit, 12-bit"Audio Support: HDMI In / HDBaseT Out: LPCM 5.1, LPCM 7.1, Dolby Digital, DTS 5.1, Dolby Digital+, Dolby TrueHD, DTS-HD Master Audio HDCP 1.4/2.2 HDCP 2.2 compliant and supports EDID filtering Bidirectional extension of both RS-232 and IR control commands | 1 | No. | 349138 | 349138 |  | MR
63 | Supply, Installation, Testing & Commessioning of HDMI to USB Video capture with HDMI bypass HDMI input and output with 4K@60Hz support, DVI 1.0 compatible HDCP 2.2 and HDCP 1.x compliant Automatically scales 4K sources to 1080p for USB capture Unit may be powered directly via USB 3.0 Supports video timing stabilization to help ensure a reliable and stable USB capture stream Capturing over USB 3.0 allows uncompressed video and audio data capture (up to 1080p, LPCM 2.0) Supports capturing 2 channel digital audio from either HDMI (LPCM 2.0) or the 3.5mm analog audio input (selectable via configuration software) Compliance with the UAC (USB Audio Class) and UVC (USB Video Class) standards, allows the unit to support most common capture and video streaming software Inputs : 1x HDMI, 1x 3.5mm , Output : 1x HDMI, 1x USB Type-B | 1 | No. | 207116 | 207116 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
64 | Supply, Installation, Testing & Commessioning of secure, high performance control processor, Having ethernet port of 100/1000 Mbps, auto switching, auto negotiating, auto discovery, full/half duplex, industry-standard TCP/IP stack, DHCP, SSL, TLS, IEEE 802.1xX, SNMP, HTTPS. Having minimum Memory SDRAM 1 GB, Flash 8 GB, and External Storage Support, Minimum Control ports of 7no's RELAY OUTPUT, Min 7 no’s I/O port., 1 x Bidirectional RS-232/422/485 port, Minimum 2 x Bidirectional RS-232 ports, Should have BACnet™ for integration (internal or by additional hardware) with existing building management systems like Centralized HVAC, security fire, Should be able to control the complete programmed system, from the IT laptop or PC, comply to CE, UL, FCC. | 1 | No. | 266291 | 266291 |  | MR
65 | Supply , Installation , Testing & Commissioning of Touch Control tabletop panel of minimum 10" , capacitive widescreen active‑matrix color display , 1024 x 600 display resolution , Minimum 5 backlit soft‑touch buttons , PoE (Power over Ethernet) , built‑in light sensor , compatible with control processor and complete as per the specifications. | 1 | No. | 195280 | 195280 |  | MR
66 | Supply , Installation , Testing & Commissioning of PTZ Camera with 2K Resolution with 1/2.8 inch or higher high quality CMOS sensor , 2592 x 1944@3FPS super high quality video ,10 x or more zoom with 10x or more digital zoom, Pan Range: 340deg or more With USB2.0, 5 or more preset position and complete as per the specifications. | 4 | Nos. | 112434 | 449736 |  | MR
67 | Supply , Installation , Testing & Commissioning of HDMI Interface Cable with High-speed, 24k gold-plated 19-pin Type A connectors High-flex CL3-rated jacket Supports 4K60 4:4:4 video, 18 Gbps , , Supports 4K60 4:2:0 and 4K30 4:4:4 video , RoHS compliant, Length 1.8 meter complete as per the technical specifications . | 18 | Nos. | 2190 | 39420 |  | MR
68 | Supply and Laying of Shielded Twisted Pair Cable , Conductor Metal: Solid Bare Copper with 23 AWG Color Code: Blue/ Grey ( or any combination) , Jacket Material: PVC UL94V-0 and complete as per the specifications. | 800 | Mtrs. | 148 | 118400 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
69 | Supply , Installation , Testing & Commissioning of Equipment Rack of Size 32 u , 600 mm (W) , 800 mm (D) with front door , Front door lockable with tinted glass / Fiber sheet , Rear door lockable , Top cover with cable entry provision , Fully vented with blowers , Castors with foot operated brakes , 19″ mounting angles at front and rear , 10 x 16amp sockets and complete as per the specifications. | 1 | No. | 53258 | 53258 |  | MR
Sound System
70 | Supply , Installation , Testing & Commissioning of MAIN LCR Line Source Speaker:- Line Array Speaker LF - 700W RMS (8 ohms) HF - 110W Continuous RMS(16 ohms,) or above, LF Custom made 2 x 10” driver ferrite magnet, 2.5” in/out Voice coil + 1.5" exit HF or better, Frequency Response 50Hz-18khz, Average Sensitivity - 99dB/W/m LF, 109dB/W/m HF or better, Max SPL 136db peak or above, Nominal Directivity - 100° x 15° , Cabinet - CNC made with tongue & grove assembly 15 and 18mm Baltic birch plywood and complete as per the specifications. | 12 | Nos. | 218951 | 2627412 |  | MR
71 | Supply , Installation , Testing & Commissioning of Array Frame:- Compact crossbow flying frame for IWAC210,integrated rigging, up to 2.5T load and complete as per the specifications. | 3 | Nos. | 112434 | 337302 |  | MR
72 | Supply , Installation , Testing & Commissioning of Subwoofer:- Subwoofer System with minimum 2 x 18” (4” VC), or above , Frequency Response 34Hz-1500hz or better, Max SPL not less than 140db / 1m, with continuous RMS power of 2600 Watt RMS with programmed power of 5200Watt RMS & peak power of 10400 Watt RMS, with sensitivity of 100 dB, or Better, Nominal Impedance : 4ohms, in birch plywood paint finish etc. and complete as per the specifications. | 2 | Nos. | 174569 | 349138 |  | MR
73 | Supply , Installation , Testing & Commissioning of Stage Monitor:- 2-way loudspeaker System with minimum 1 x 15” (3” VC), or above LF, HF - 1" exit Frequency Response 48Hz-22khz, or better, Max SPL not less than 133db / 1m, with continuous RMS power of 500 - 600 Watt RMS with programmed power of 1000– 1200Watt RMS & peak power of 2000 - 2400 Watt RMS, with sensitivity of 98 dB, or Better, Nominal Impedance : 8 ohms, nominal dispersion : 80 x 50 or better, in birch plywood paint finish etc. and complete as per the specifications. | 4 | Nos. | 76929 | 307716 |  | MR
74 | Supply , Installation , Testing & Commissioning of Front Fill Speaker:- 2-way full range, 120W RMS, 12 ohms, LF Custom made 1 x 6” or above Coaxial driver ferrite magnet, 1.5” in/out Voice coil + 0.75" exit HF, Frequency Response 65Hz-22khz, or better, Average Sensitivity - 90dB/W/m or better, Max SPL 117db peak or better ,Nominal Directivity - 85° conical or better),in birch plywood paint finish with wall mount bracket etc. and complete as per the specifications. | 4 | Nos. | 33730 | 134920 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
75 | Supply , Installation , Testing & Commissioning of Surround Speaker:- 2-way loudspeaker System with minimum 1 x 8” (2” VC), or above LF, HF - 1" exit Frequency Response 52Hz-22khz, or better, Max SPL not less than 121db / 1m, with continuous RMS power of 200 - Watt RMS with programmed power of 400Watt RMS & peak power of 800 Watt RMS, with sensitivity of 92 dB, or Better Nominal Impedance : 8 /12 ohms, nominal dispersion : 80 conical or better, in birch plywood paint finish with wall mount bracket etc. and complete as per the specifications. | 12 | Nos. | 38464 | 461568 |  | MR
76 | Supply , Installation , Testing & Commissioning of Green Room / Control Room Speaker:- 2-way full range, 120W RMS, 12 ohms, LF Custom made 1 x 6” or above Coaxial driver ferrite magnet, 1.5” in/out Voice coil + 0.75" exit HF, Frequency Response 65Hz-22khz, or better, Average Sensitivity - 90dB/W/m or better, Max SPL 117db peak or better ,Nominal Directivity - 85° conical or better),in birch plywood paint finish with wall mount bracket etc. and complete as per the specifications. | 2 | Nos. | 32547 | 65094 |  | MR
77 | Supply , Installation , Testing & Commissioning of Amplifier for Line Array and Subwoofer:- Professional Four channel Power amplifier, 4 x 800W @ 8 ohms or above, 4 x 1300W @ 4 ohms or above, Sensitivity - 2.03v or better, Frequency Response: 20- 25000Hz, Input Impedance - 20K, Crosstalk - >75dB or better, S/ N ratio 112dB or better, Damping Factor - 800 or better, THD - < 0.05% , Slew Rate - 60V / us or better and complete as per the specifications. | 4 | Nos. | 289962 | 1159848 |  | MR
78 | Supply , Installation , Testing & Commissioning of Amplifier for Stage Monitor :- Professional Four channel Power amplifier, 4 x 750W @ 8 ohms or above, 4 x 1100W @ 4 ohms or above, Sensitivity - 1.6v or better, Frequency Response: 10- 25000Hz, Input Impedance - 20K, Crosstalk - >70dB or better, S/ N ratio - > 110dB or better, Damping Factor - 500 or better, THD - < 0.05% , Slew Rate - 30V / us or better and complete as per the specifications. | 1 | No. | 159775 | 159775 |  | MR
79 | Supply , Installation , Testing & Commissioning of Amplifier for Surround , Front Fill and Green / Control Room Speaker:- Professional Dual channel Power amplifier, 2x 400W @ 8 ohms or above, 2 x 600W @ 4 ohms or above, Sensitivity - 0.775v ,Frequency Response: 20- 20000Hz , Input Impedance - 20K, Crosstalk - >65dB, S/ N ratio - > 110dB or better, Damping Factor - 350 or better, THD - < 0.1% , Slew Rate - 15V / us or better and complete as per the specifications. | 6 | Nos. | 57401 | 344406 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
80 | Supply , Installation , Testing & Commissioning of AV Receiver:- Supply, installation, testing & commissioning of 11.2 Channel Full 4K Ultra HD Network AV Surround Processor with, Dolby Atmos and DTS: x (up to 7.1.4) and auro-3d > immersive 3D sound with effects from overhea,11.2-channel balanced XLR outputs include outputs for 2 powered subwoofers and complete as per the specifications. | 1 | No. | 207116 | 207116 |  | MR
81 | Supply , Installation , Testing & Commissioning of Mixer:- 32 total inputs mixing console with Effects, Mid-sweep 3-band mono channel EQ, 4-band stereo channel EQ, 4 buses for flexible signal routing: main stereo bus, four group buses, six auxiliary buses, and send buses for the two internal effect processors etc. and complete as per the specifications. | 1 | No. | 171610 | 171610 |  | MR
82 | Supply , Installation , Testing & Commissioning of Digital Controller:- 4 in x 8 Out Networkable Loudspeaker Management System, High precision 32-bit floating point TEXAS INSTRUMENT DSP (48kHz sampling rate)24-bit D/A converters with 118B dynamic range and audiophile grade preamps, On each output: Routing, Delay, Gain, HPF and LPF filters (up to 48dB/oct), 8 filters (PEQ and Shelving), Compressor / Limiter (Threshold, Attack, Release, Ratio) and complete as per the specifications. | 1 | No. | 195280 | 195280 |  | MR
83 | Supply , Installation , Testing & Commissioning of Gooseneck Microphone:- 16.5" Gooseneck cardioid Microphone, polar pattern cardioid, Frequency Range 70-16000 Hz, Sensitivity14.1mV/Pa, Dynamic Range >106dB. Complete with mic base unit etc. and complete as per the specifications. | 2 | Nos. | 23079 | 46158 |  | MR
84 | Supply , Installation , Testing & Commissioning of Wireless Handheld Microphone:- Wireless Handheld Microphone with transmitter and rack mountable Receiver, UHF frequency range, selectable Operating Frequencies , 500 - 865 MHz, 100dB A- weighted, Audio Bandwidth 35 Hz to 20 kHz (+/- 2dB). True Diversity antenna compatible, Complete with adapter batteries and rack mount kit for the receiver, 30 mW min RF radiation etc. and complete as per the specifications. | 2 | Nos. | 44382 | 88764 |  | MR
85 | Supply , Installation , Testing & Commissioning of Wireless Lapel Microphone:- Wireless Lapel Microphone with transmitter and rack mountable Receiver, UHF frequency range, selectable Operating Frequencies , 500 - 865 MHz, 100dB A- weighted, Audio Bandwidth 35 Hz to 20 kHz (+/- 2dB). True Diversity antenna compatible, Complete with adapter batteries and rack mount kit for the receiver, 30 mW min RF radiation etc. and complete as per the specifications. | 2 | Nos. | 44382 | 88764 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
86 | Supply , Installation , Testing & Commissioning of Wired Vocal Microphone:- Vocal Microphone, polar pattern Super cardioid, Frequency Response 80–12,000 Hz Open Circuit Sensitivity –53 dB (2.2 mV) re 1V at 1 Pa* Impedance 600 ohms Switch MagnaLock™ ON/OFF and complete as per the specifications. | 4 | Nos. | 14794 | 59176 |  | MR
87 | Supply , Installation , Testing & Commissioning of Wired Instrument Microphone:- Dynamic Instrumental Microphone, Frequency Response 60–14,000 Hz, Open Circuit Sensitivity –54 dB (1.9 mV) re 1V at 1 Pa* Impedance 600 ohms Switch MagnaLock™ ON/OFF and complete as per the specifications. | 4 | Nos. | 14794 | 59176 |  | MR
88 | Supply and Laying of Microphone Cable:- Laying & Fixing of of Microphone lines high grade, professional low-noise, 2 core high conductivity PVC insulated in PVC jacket, shielded copper cable with Di- electric insulator both end with XLR m/f connector and complete as per the specifications. | 2600 | Mtrs. | 148 | 384800 |  | MR
89 | Supply and Laying of Speaker Cable:- Laying & Fixing of speaker lines: 4 core, 1.5 sq. mm high definition speaker cable, PVC insulated in PVC jacket laid in existing conduits and complete as per the specifications. | 300 | Mtrs. | 130 | 39000 |  | MR
90 | Supply and Laying of Speaker Cable:- Laying & Fixing of speaker b lines: 2 core, 2.5 sq. mm high definition speaker cable, PVC insulated in PVC jacket laid in existing conduits and complete as per the specifications. | 1500 | Mtrs. | 172 | 258000 |  | MR
91 | Supply , Installation , Testing & Commissioning of Floor Junction Box:- floor junction boxes on the stage for the various mic inputs with xlr inputs on the boxes and complete as per the specifications. | 8 | Nos. | 7693 | 61544 |  | MR
92 | Supply , Installation , Testing & Commissioning of Floor Microphone Stand:- Floor Standing Microphone Stand etc. and complete as per the specifications. | 4 | Nos. | 3373 | 13492 |  | MR
93 | Supply , Installation , Testing & Commissioning of Table Top Microphone Stand:- Table Top Microphone Stand etc. and complete as per the specifications. | 4 | Nos. | 1716 | 6864 |  | MR
Stage Lighting
94 | Supply , Installation , Testing & Commissioning of 200W Full Power light Source, Warm Cold: 3200K and Cold White: 5600K.6 meters effective range,10000 hours lifespan. 2/4 Channels [4 Control Mode] Automatic/ Rapid Response Sound Active/ Master-Slave Mode / DMX-512 remote controller [Features] Y axis 180 degrees and stable mounting brackets ensure the light can be wall hanging or up lighting. [Occasion] Professional Stage lighting kits, Super bright for Stage show, Home Party, Street live, Cinema, photography , IP 20 protection and complete as per the specifications. | 10 | Nos. | 20712 | 207120 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
95 | Supply , Installation , Testing & Commissioning of 200watt Plano Convex Spot Light with Having CRI TLCI Values above 95 High precision steady color ,No heat, DmX 512 dimming with 2 Channel Beam Angle 15°/ 25° / 45°, 0 ~ 100%, Powder coated Black finish housing Rigidly built pressure die-casted Aluminum body LED Easy view display Flicker Free for high FPS Smooth fade in and Fade out Data DmX through 3 / 5 Pin XLR’s Total Power Consumption of 200W IP20 protection and complete as per the specifications. | 6 | Nos. | 53258 | 319548 |  | MR
96 | Supply , Installation , Testing & Commissioning of LED Fresnel Light with VOLTAGES: 100~240V AC，50/60Hz, POWER CONSUMPTION: 179.6W @ 220V, LIGHT SOURCE: Citizen 200W LED, COLOR TEMPERATURE: 3000K, LUMENS: 2982lm~5845lm, BEAM ANGLE: 30°~87°, DIMMER: 1~100% linearly adjustable, CONTROL: DMX512, 5 pin interfaces , 1 channel in standard mode, WORK ENVIRONMENT TEMPERATURE: -20°C~40°C, HOUSING: High-intensity extruding aluminum, IP20, WEIGHT: 6kg, OTHER FUNCTIONS: Low noise(<30dB), CRI:83, Lumens for high light 6000lm, Ideal for television studios, theatres, various conference rooms, multifunctional halls and other locations as functional lighting and complete as per the specifications. | 6 | Nos. | 57696 | 346176 |  | MR
97 | Supply , Installation , Testing & Commissioning of 24 x 3W/ 36x3W LED Long BAR Light with Electrical: Voltage: AC100~240V... 50/60Hz, Rated Power: 72W, LED: 24* RGB X 3 W, Beam Angle: 40°. Functions: RGBW color mixing / Custom programs / Strobe / white Balance / RGB and complete as per the specifications. | 6 | Nos. | 46453 | 278718 |  | MR
98 | Supply , Installation , Testing & Commissioning of 200 watt LED Profile Spot with Lamp power: 200 watt, Power Supply 110v-220V 50Hz, Beam Angle 19 Degree, Control: DMX Auto rum and master/Slave,CRI:>90,Colour Temperature: 3200K, Shutter: Beam Shaping shutter or plasticgobo projection assembly, IP Rate:20 and complete as per the specifications. | 6 | Nos. | 51483 | 308898 |  | MR
99 | Supply , Installation , Testing & Commissioning of 100 W Full Power light Source, Warm Cold: 3200K and Cold White: 5600K.6 meters effective range,10000 hours lifespan. 2/4 Channels [4 Control Mode] Automatic/ Rapid Response Sound Active/ Master-Slave Mode / DMX-512 remote controller [Features] Y axis 180 degrees and stable mounting brackets ensure the light can be wall hanging or up lighting. [Occasion] Professional Stage lighting kits, Super bright for Stage show, Home Party, Street live, Cinema, photography , IP 20 protection and complete as per the specifications. | 8 | Nos. | 18640 | 149120 |  | MR
100 | Supply , Installation , Testing & Commissioning of LED PAR Light with 54 x 3W high quality LED’s , 100-120V and 200- 240V AC, 50/60Hz (210W@220V), RGBW color mixing +3200K ~ 10000K linearly adjustable color temperature, 0- 100% linearly adjustable dimmer, Strobe 0~20 F.P.S, Beam Angle: 45°, LED board temperature display, DMX mode, display setting status, operation mode can be transmitted by synchronous control, Standard, Type:LED-354RGB and complete as per the specifications. | 14 | Nos. | 23079 | 323106 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
101 | Supply , Installation , Testing & Commissioning of Moving Head Wash 30W * 19 LEDs (RGBW 4-in-1), Zoom range 3° - 50° , Individual control of LED rings Small, compact and light weight Linear CTO from 3200K - 7200K, Light source: 30W (RGBW 4-in-1) 19 LEDs (White/Amber LED optional), Expected average lifetime: 50000 hours, Beam angle: Zoom range 3° - 50°, Photometric Total Output (Lumen): 4830 lumens narrow/6450 lumens wide and complete as per the specifications. | 4 | Nos. | 100599 | 402396 |  | MR
102 | Supply , Installation , Testing & Commissioning of 300W Beam, Spot, Wash (3 in 1) Moving Head with Input Voltage: AC90/240C, 50-80Hz, Lamp: 15R 300W (OSRAM), Power: 500W, Life Time: 2200 hrs., DMX Channels: 16CH / 24CH / 30CH, Pan: 540° (16bit), Tilt: 245° (16bit), Color Wheel: 13 dichroic filters + white, Rotating Gobo Wheel: 9 Bidirectional and index able gobos, Static Gobo Wheel: 14 fixed gobos at variable rotation, Strobe: 0-13f/s, random or pulse flash, speed adjustable strobe macro function, Dimmer: 0-100% linear light dimming and complete as per the specifications. | 4 | Nos. | 159775 | 639100 |  | MR
103 | Supply , Installation , Testing & Commissioning of 3000W Smoke Machine with Power: AC230V/Ac240V, 50Hz-60Hz, Heater: 3000W, Output: 40,000 cu.ft/min., First Heat-up Time: 12 min., Tank Capacity: 6 Liter, Fluid Consumption Rate: 5 min./liter (100% Output), DMX: On Board, Remote operated, Ideal for very large venues, outdoor event, movie production or for fire training concept. Type:S-3000 and complete as per the specifications. | 2 | Nos. | 45565 | 91130 |  | MR
104 | Supply , Installation , Testing & Commissioning of Lighting Control Console: with Internal Flash Drive, similar in functionality to a hard disk but faster and more rugged. Provides enough storage for:- The entire Fixture Library of more than 3,000 files, Over a hundred show files, Removable external Memory Stick, Cache the entire Fixture library of more than 3,000 files, Improved method of Fixture selection for Patching, New Locate Fixture button, Fixture Selects (selecting the top row of faders), 2048 Channels, 240 Intelligent Fixtures, 240 Dimmer Control Channels, Theatrical Plotting and Playback functions, Shape Generator for instant creation of patterns and effects, 15 Playback Masters controlling 450 memories, chases or cue lists, MIDI and Bass, Mid, Treble sound to light triggers, Color VGA output fitted as standard and complete as per the specifications. | 1 | No. | 325467 | 325467 |  | MR
105 | Supply , Installation , Testing & Commissioning of "J" Clamp made out of MS strip with nut bolt painted in black cloud, Load capacity 60KG and complete as per the specifications. | 80 | Nos. | 414 | 33120 | Item to be executed on urgent basis because of resigned of M/s Aslam builders, Agreement No: EE/JED/14 of 2021-22. Due to This reason Civil Work heldup. | MR
106 | Supply , Installation , Testing & Commissioning of Light Point Wiring from Distribution Board to be provided near stage to various stage light fixtures with 2.5 Sq. mm 3 Core PVC Insulated and PVC Sheathed Cable including Cable Tray of suitable size for laying these wires on the tray including 20 amps metallic clad sockets/ 15 Amp Socket to direct points with box at top and complete as per the specifications. | 30 | Nos. | 6154 | 184620 |  | MR
107 | Supply , Installation , Testing & Commissioning of DMX 2 No. 26500 53000 Splitter with one DMX input and 6 buffered outputs and 3 pin / 5 pin XLR connectors. Type: SPL-6/2 and complete as per the specifications. | 1 | No. | 17161 | 17161 |  | MR
108 | Supply and Laying of 2 core shielded DMX Cable and complete as per the specifications. | 1000 | Mtrs. | 133 | 133000 |  | MR
109 | Supply , Installation , Testing & Commissioning of Electrical Panel made out of CRC sheet painted in gray color, wall mountable with 32 amp S/P MCB- 40, 63 amp 4 pole MCB, Indicator, bus bar and required accessories and complete as per the specifications. | 1 | No. | 171610 | 171610 |  | MR
CC TV System
110 | Supply and Laying of CAT 6 UTP cable 23 AWG solid copper conductors with flame retardant properties, in compliance to relevant IEC standards and complete as per the specifications. | 1000 | Mtrs. | 77 | 77000 |  | MR
| Total |  |  |  | 29532360 |  | 13.2412
1 | The Statement contains 4 item only
2 | The rate are net and not subjected to any enchancement / rebate
3 | The quantities are aproximate and the payment shall be made as per actual quantities executed at site and undue benefit has been given to the contractor
This Extra item Statement No- II ( Electrical) amounting to Rs: 2,95,32,360/- ( Two Crore Ninty five Lac thirty two Thousand Three Hundred Sixty only) which is 13.24 % of Tender amount ( Civil ) i.e 22,30,33,051 /- is hereby approved by this office
| JE ( E) AE ( E) |  | AE (P) |  | EE (E )

## DSR AR
DSR No | Rate | Add GST cost index @ 6.33 % | Total After Adding GST Factor | Less As per Agreement @ 7% | Grand Total
1.3.3 | 1845 | 116.7885 | 1961.7885 | 137.3252 | 1824
1.54.3 | 1094 | 69.2502 | 1163.2502 | 81.4275 | 1082
1.7.1 | 327 | 20.6991 | 347.6991 | 24.3389 | 323
1.7.4 | 589 | 37.2837 | 626.2837 | 43.8399 | 582
1.7.9 | 924 | 58.4892 | 982.4892 | 68.7742 | 914
1.7.10 | 1166 | 73.8078 | 1239.8078 | 86.7865 | 1153
1.5 | 433 | 27.4089 | 460.4089 | 32.2286 | 428
1.6 | 662 | 41.9046 | 703.9046 | 49.2733 | 655
1.20.1 | 223 | 14.1159 | 237.1159 | 16.5981 | 221
1.20.2 | 256 | 16.2048 | 272.2048 | 19.0543 | 253
1.20.3 | 326 | 20.6358 | 346.6358 | 24.2645 | 322
1.20.4 | 470 | 29.751 | 499.751 | 34.9826 | 465
1.21.2 | 145 | 9.1785 | 154.1785 | 10.7925 | 143
1.21.3 | 184 | 11.6472 | 195.6472 | 13.6953 | 182
1.26 | 40 | 2.532 | 42.532 | 2.9772 | 40
1.19 | 47 | 2.9751 | 49.9751 | 3.4983 | 46
1.18.2 | 38 | 2.4054 | 40.4054 | 2.8284 | 38
1.24.7 | 148 | 9.3684 | 157.3684 | 11.0158 | 146
1.24.6 | 148 | 9.3684 | 157.3684 | 11.0158 | 146
1.25 | 369 | 23.3577 | 392.3577 | 27.465 | 365
1.27.1 | 298 | 18.8634 | 316.8634 | 22.1804 | 295
1.31 | 477 | 30.1941 | 507.1941 | 35.5036 | 472
1.32 | 586 | 37.0938 | 623.0938 | 43.6166 | 579
1.57 | 727 | 46.0191 | 773.0191 | 54.1113 | 719
DSR No | Rate | Add GST cost index @ 6.33 % | Total After Adding GST Factor | Less As per Agreement @ 7% | Grand Total
18.6.2 | 3804 | 240.7932 | 4044.7932 | 283.1355 | 3762
18.7.6 | 1885 | 119.3205 | 2004.3205 | 140.3024 | 1864
18.7.7 | 2555 | 161.7315 | 2716.7315 | 190.1712 | 2527
18.7.8 | 3574 | 226.2342 | 3800.2342 | 266.0164 | 3534
18.12.7 | 39332 | 2489.7156 | 41821.7156 | 2927.5201 | 38894
18.12.6 | 22762 | 1440.8346 | 24202.8346 | 1694.1984 | 22509
18.12.4 | 10696 | 677.0568 | 11373.0568 | 796.114 | 10577
18.14.7 | 17786 | 1125.8538 | 18911.8538 | 1323.8298 | 17588
18.14.4 | 7691 | 486.8403 | 8177.8403 | 572.4488 | 7605
18.9.1 | 7646 | 483.9918 | 8129.9918 | 569.0994 | 7561
18.10.1 | 7646 | 483.9918 | 8129.9918 | 569.0994 | 7561
18.11.4 | 4982 | 315.3606 | 5297.3606 | 370.8152 | 4927
18.11.5 | 6667 | 422.0211 | 7089.0211 | 496.2315 | 6593
18.11.6 | 8960 | 567.168 | 9527.168 | 666.9018 | 8860
18.13 | 1321 | 83.6193 | 1404.6193 | 98.3234 | 1306
18.19.3 | 9455 | 598.5015 | 10053.5015 | 703.7451 | 9350
18.24.2 | 45002 | 2848.6266 | 47850.6266 | 3349.5439 | 44501
18.18.1 | 2416 | 152.9328 | 2568.9328 | 179.8253 | 2389
16.8 | 1196 | 75.7068 | 1271.7068 | 89.0195 | 1183
18.15.3 | 11144 | 705.4152 | 11849.4152 | 829.4591 | 11020
DSR No | Rate | Add GST cost index @ 6.33 % | Total After Adding GST Factor | Less As per Agreement @ 7% | Grand Total
17.5.1 | 359 | 22.7247 | 381.7247 | 26.7207 | 355
17.5.3.1 | 54 | 3.4182 | 57.4182 | 4.0193 | 53
17.5.4 | 53 | 3.3549 | 56.3549 | 3.9448 | 52
1.20.2 | 256 | 16.2048 | 272.2048 | 19.0543 | 253
1.53.1 | 57 | 3.6081 | 60.6081 | 4.2426 | 56
DSR No | Rate | Add GST cost index @ 6.33 % | Total After Adding GST Factor | Less As per Agreement @ 7% | Grand Total
5.12 | 1309 | 82.8597 | 1391.8597 | 97.4302 | 1294
5.11 | 1265 | 80.0745 | 1345.0745 | 94.1552 | 1251
5.1 | 1230 | 77.859 | 1307.859 | 91.5501 | 1216
5.9 | 1170 | 74.061 | 1244.061 | 87.0843 | 1157
5.8 | 1108 | 70.1364 | 1178.1364 | 82.4695 | 1096
5.7 | 1022 | 64.6926 | 1086.6926 | 76.0685 | 1011
5.6 | 865 | 54.7545 | 919.7545 | 64.3828 | 855
5.5 | 707 | 44.7531 | 751.7531 | 52.6227 | 699
5.4 | 588 | 37.2204 | 625.2204 | 43.7654 | 581
5.3 | 466 | 29.4978 | 495.4978 | 34.6848 | 461
5.2 | 331 | 20.9523 | 351.9523 | 24.6367 | 327
5.1 | 245 | 15.5085 | 260.5085 | 18.2356 | 242
16.12.2.1 | 1058 | 66.9714 | 1124.9714 | 78.748 | 1046
16.12.2.2 | 1229 | 77.7957 | 1306.7957 | 91.4757 | 1215
16.12.2.3 | 1629 | 103.1157 | 1732.1157 | 121.2481 | 1611
16.23.1 | 754 | 47.7282 | 801.7282 | 56.121 | 746
16.23.2 | 968 | 61.2744 | 1029.2744 | 72.0492 | 957
16.21 | 708 | 44.8164 | 752.8164 | 52.6971 | 700
16.13 | 7046 | 446.0118 | 7492.0118 | 524.4408 | 6968
16.15 | 9105 | 576.3465 | 9681.3465 | 677.6943 | 9004
16.16 | 5910 | 374.103 | 6284.103 | 439.8872 | 5844
16.17 | 12184 | 771.2472 | 12955.2472 | 906.8673 | 12048
16.18 | 8121 | 514.0593 | 8635.0593 | 604.4542 | 8031
16.20.1 | 10659 | 674.7147 | 11333.7147 | 793.36 | 10540
16.20.2 | 9948 | 629.7084 | 10577.7084 | 740.4396 | 9837

## AR Market
Item No 11(a)
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | RJ- 45 socket cat-6 with shetter (Make: Legrand- Myrius) ( Cat no 6730 81) (Rs. 1028/- Less 18% GST ) | 1 | No | 871.1864 | each | 871.1864
| Less @ 25 % |  |  |  |  | 217.7966
| Total |  |  |  |  | 653.3898
i) | Cartage @2 % | 2% | of A1 |  |  | 13.0678
| Total A |  |  |  |  | 666.4576
B | Labour
i) | ITC | 4% | of A1 |  |  | 26.6583
| Total A+B |  |  |  |  | 693.1159
C | GST @ M.F 0.2127 |  |  |  |  | 147.4258
| Total (A+B+C) |  |  |  |  | 840.5417
D | Overhead & profit @ | 15% |  |  |  | 126.0813
| Total (A+B+C+D) |  |  |  |  | 966.6229
[5 empty] | SAY | 967
Item No 16
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | Modular GI box for 8 module i/cModular base & cover plate for 8 module | 1 | No | 454 | each | 454
| 3 pin 5 / 6 amps modular socket outlet, ISI marked | 3 | No | 122 | each | 366
| S.P. 15 / 16 amps, one way modular switch, ISI marked | 1 | No | 156 | each | 156
| Total (A 1) |  |  |  |  | 976
[5 empty] | SAY | 976
Item No 29
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | hose cabinet ( 900 mm x 600 mm x 500 mm ) outdoor type ( LP Rs.15000 /- ) Make - Life Guard | 1 | No | 15000 | each | 15000
| Less @ 25 % |  |  |  |  | 3750
| Total |  |  |  |  | 11250
i) | Cartage @2 % | 2% | of A1 |  |  | 225
| Total A |  |  |  |  | 11475
B | Labour
i) | Welder, Grade 1 | 0.2 | days | 788 |  | 157.6
| Khallasi - | 0.2 | days | 595 |  | 119
| Total A+B |  |  |  |  | 11751.6
C | GST @ M.F 0.2127 |  |  |  |  | 2499.5653
| Total (A+B+C) |  |  |  |  | 14251.1653
D | Overhead & profit @ | 15% |  |  |  | 2137.6748
| Total (A+B+C+D) |  |  |  |  | 16388.8401
[5 empty] | SAY | 16389
Item No 30
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | standard fireman's axe with heavy insulated rubber handle ( LP Rs.875 /- ) Make - Life Guard | 1 | No | 875 | each | 875
| Less @ 25 % |  |  |  |  | 218.75
| Total |  |  |  |  | 656.25
i) | Cartage @2 % | 2% | of A1 |  |  | 13.125
| Total A |  |  |  |  | 669.375
B | Labour
i) | Welder, Grade 1 | 0 | days | 788 |  | 0
| Khallasi - | 0 | days | 595 |  | 0
| Total A+B |  |  |  |  | 669.375
C | GST @ M.F 0.2127 |  |  |  |  | 142.3761
| Total (A+B+C) |  |  |  |  | 811.7511
D | Overhead & profit @ | 15% |  |  |  | 121.7627
| Total (A+B+C+D) |  |  |  |  | 933.5137
[5 empty] | SAY | 934
Item No 38
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | Providing and fixing of lockcable 12U wall /Floor Mounted Rack with Cable Manager for distribution, mounting of patch panels hubs, switches etc complete as required. | 1 | Each | 5800 | Each | 5800
| Networking Cable Manager | 2 | Each | 570 | Each | 1140
| Total |  |  |  |  | 6940
| Less @ 25 % |  |  |  |  | 1735
| Total |  |  |  |  | 5205
i) | Cartage @2 % | 2% | of A1 |  |  | 104.1
| Total A |  |  |  |  | 5309.1
B | Labour
i) | 1001 Wireman | 0.5 | days | 788 |  | 394
| 1007 Khallasi | 0.5 | days | 595 |  | 297.5
| Total A+B |  |  |  |  | 6000.6
C | GST @ M.F 0.2127 |  |  |  |  | 1276.3276
| Total (A+B+C) |  |  |  |  | 7276.9276
D | Overhead & profit @ | 15% |  |  |  | 1091.5391
| Total (A+B+C+D) |  |  |  |  | 8368.4668
[5 empty] | SAY | 8368
Item No 39
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | 24 Ports, Patch Panel | 1 | Each | 4999 | Each | 4999
| Less @ 25 % |  |  |  |  | 1249.75
| Total |  |  |  |  | 3749.25
i) | Cartage @2 % | 2% | of A1 |  |  | 74.985
| Total A |  |  |  |  | 3824.235
B | Labour
i) | 1001 Wireman | 0.5 | days | 788 |  | 394
| 1007 Khallasi | 0.5 | days | 595 |  | 297.5
| Total A+B |  |  |  |  | 4515.735
C | GST @ M.F 0.2127 |  |  |  |  | 960.4968
| Total (A+B+C) |  |  |  |  | 5476.2318
D | Overhead & profit @ | 15% |  |  |  | 821.4348
| Total (A+B+C+D) |  |  |  |  | 6297.6666
[5 empty] | SAY | 6298
Item No 41
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | refrigerant T/Y-Joint fittings and headers to all indoor units ( Quotation Price Rs:7,800/- ) | 1 | No | 7800 | each | 7800
| Less @ 25 % |  |  |  |  | 1950
| Total |  |  |  |  | 5850
i) | Cartage @2 % | 2% | of A1 |  |  | 117
| Total A |  |  |  |  | 5967
B | Labour
i) | ITC | 4% | of A1 |  |  | 238.68
| Total A+B |  |  |  |  | 6205.68
C | GST @ M.F 0.2127 |  |  |  |  | 1319.9481
| Total (A+B+C) |  |  |  |  | 7525.6281
D | Overhead & profit @ | 15% |  |  |  | 1128.8442
| Total (A+B+C+D) |  |  |  |  | 8654.4724
[5 empty] | SAY | 8654
Item No 43 (a)
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | 50 MM Dia ( Quotation Price Rs:430/- ) | 1 | Mtr | 430 | Meter | 430
| Total |  |  |  |  | 430
| Less @ 25 % |  |  |  |  | 107.5
| Total |  |  |  |  | 322.5
i) | Cartage @2 % | 2% | of A1 |  |  | 6.45
| Total A |  |  |  |  | 328.95
B | Labour
i) | ITC | 4% | of A1 |  |  | 13.158
| Total A+B |  |  |  |  | 342.108
C | GST @ M.F 0.2127 |  |  |  |  | 72.7664
| Total (A+B+C) |  |  |  |  | 414.8744
D | Overhead & profit @ | 15% |  |  |  | 62.2312
| Total (A+B+C+D) |  |  |  |  | 477.1055
[5 empty] | SAY | 477
Item No 43 (b)
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | 32 MM Dia ( Quotation Price Rs:365/- ) | 1 | Mtr | 365 | Meter | 365
| Total |  |  |  |  | 365
| Less @ 25 % |  |  |  |  | 91.25
| Total |  |  |  |  | 273.75
i) | Cartage @2 % | 2% | of A1 |  |  | 5.475
| Total A |  |  |  |  | 279.225
B | Labour
i) | ITC | 4% | of A1 |  |  | 11.169
| Total A+B |  |  |  |  | 290.394
C | GST @ M.F 0.2127 |  |  |  |  | 61.7668
| Total (A+B+C) |  |  |  |  | 352.1608
D | Overhead & profit @ | 15% |  |  |  | 52.8241
| Total (A+B+C+D) |  |  |  |  | 404.9849
[5 empty] | SAY | 405
Item No 43 (c)
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | 25 MM Dia ( Quotation Price Rs:296/- ) | 1 | Mtr | 296 | Meter | 296
| Total |  |  |  |  | 296
| Less @ 25 % |  |  |  |  | 74
| Total |  |  |  |  | 222
i) | Cartage @2 % | 2% | of A1 |  |  | 4.44
| Total A |  |  |  |  | 226.44
B | Labour
i) | ITC | 4% | of A1 |  |  | 9.0576
| Total A+B |  |  |  |  | 235.4976
C | GST @ M.F 0.2127 |  |  |  |  | 50.0903
| Total (A+B+C) |  |  |  |  | 285.5879
D | Overhead & profit @ | 15% |  |  |  | 42.8382
| Total (A+B+C+D) |  |  |  |  | 328.4261
[5 empty] | SAY | 328
Item No 50
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | supply air Jet Nozzles of powder coated aluminum ( Quotation Price Rs:6673/- ) | 1 | Each | 6673 | Nos | 6673
| Total |  |  |  |  | 6673
| Less @ 25 % |  |  |  |  | 1668.25
| Total |  |  |  |  | 5004.75
i) | Cartage @2 % | 2% | of A1 |  |  | 100.095
| Total A |  |  |  |  | 5104.845
B | Labour
i) | ITC | 4% | of A1 |  |  | 204.1938
| Total A+B |  |  |  |  | 5309.0388
C | GST @ M.F 0.2127 |  |  |  |  | 1129.2326
| Total (A+B+C) |  |  |  |  | 6438.2714
D | Overhead & profit @ | 15% |  |  |  | 965.7407
| Total (A+B+C+D) |  |  |  |  | 7404.0121
[5 empty] | SAY | 7404
Item No 53
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | extruded aluminum volume control damper with blades ( Quotation Price Rs:10,384/- ) | 1 | Sqmt | 10384 | Sqmt | 10384
| Total |  |  |  |  | 10384
| Less @ 25 % |  |  |  |  | 2596
| Total |  |  |  |  | 7788
i) | Cartage @2 % | 2% | of A1 |  |  | 155.76
| Total A |  |  |  |  | 7943.76
B | Labour
i) | ITC | 4% | of A1 |  |  | 317.7504
| Total A+B |  |  |  |  | 8261.5104
C | GST @ M.F 0.2127 |  |  |  |  | 1757.2233
| Total (A+B+C) |  |  |  |  | 10018.7337
D | Overhead & profit @ | 15% |  |  |  | 1502.81
| Total (A+B+C+D) |  |  |  |  | 11521.5437
[5 empty] | SAY | 11522
Item No 54
S.No | Description of item | Qty. |  | Rate | Unit | Amount
A 1 | Materials
i) | double layer canvas ( Quotation Price Rs 9,965/- ) | 1 | Each | 9965 | Nos | 9965
| Total |  |  |  |  | 9965
| Less @ 25 % |  |  |  |  | 2491.25
| Total |  |  |  |  | 7473.75
i) | Cartage @2 % | 2% | of A1 |  |  | 149.475
| Total A |  |  |  |  | 7623.225
B | Labour
i) | ITC | 4% | of A1 |  |  | 304.929
| Total A+B |  |  |  |  | 7928.154
C | GST @ M.F 0.2127 |  |  |  |  | 1686.3184
| Total (A+B+C) |  |  |  |  | 9614.4724
D | Overhead & profit @ | 15% |  |  |  | 1442.1709
| Total (A+B+C+D) |  |  |  |  | 11056.6432
[5 empty] | SAY | 11057

## AR AV Analaysis
AUDITORIUM - INTEGRATED VISUAL & SOUND REINFORCEMENT SYSTEM
Sr. No. | Description of Item | Qty. |  | Unit Rate | Discount @ 20% | Cost | CARTAGE @2% | Total | INSTALLATION CHARGES @ 4% | Total | GST @ 18 % ( MF 0.2127) | Total COST | Over Head Contractor profit @ 15 % | Unit Rate | ROUND UP
Video System
1 | Supply , Installation , Testing & Commissioning of Projection System with 16000 Lumens, Laser Phosphorus Projector, with WUXGA Resolution, 85% Center to Corner Uniformity, Inputs SDI In x 1, HDMI x 1 , DVI x 1, VGA x1 , RJ45 x 1, Control Ports RS232 IN / Out, Digital Link (HD Base-T) x 1, USB x 1, Remote IN / Out, Operating Temperature 0-45 C (32-113F). Lamp life 20,000 Hours, 360 degree projection installations, Logo transfer software, Portrait Installations, Geometric correction auto screen adjustment software compatible and Motorized zoom lens and complete as per the specifications. | No. | 1 | 2975000 | 595000 | 2380000 | 47600 | 2427600 | 97104 | 2524704 | 537004.5408 | 3061708.5408 | 459256.2811 | 3520964.8219 | 3520965
2 | Supply , Installation , Testing & Commissioning of Motorized Projection Screen with Matt White fabric of size 4267mm (H) x 7315 mm (W), 1.5 Gain, Black boarder on both side, Wired / Wireless remote control and complete as per the specifications. | No. | 1 | 350000 | 70000 | 280000 | 5600 | 285600 | 11424 | 297024 | 63177.0048 | 360201.0048 | 54030.1507 | 414231.1555 | 414231
3 | Supply, Installation, Testing & Commessioning of HDBaseT transmitter for HDMI and USB-C with USB Hub, Input Port: 1 x HDMI, 1 x USB-C, Output Port: 1 x HDBaseT, Data Port: 1 x USB Host, 1 x USB HUB, Signal & Control Extension: Tranmitter for AV, Power, Control & Data upto 100mtr using CATx cable, Resolution Support: 4K 60 4:4:4, Remotely powered over HDBaseT, Auto Switching: Select Active input via Hot Plug & Video Detect Technology Auto Display Control: Automatic Display On / Off control based on switcher. Control signals to display are transmitted via IP, RS-232 or CEC.,Chroma Subsampling: 4:4:4, 4:2:2, 4:2:0, Color Depth: 8-bit, 10-bit, 12-bit"Audio Support: HDMI IN / HDBaseT OUT : Dolby Digital Plus, Dolby TrueHD, DTS-HD Master Audio, Bandwidth 10 Gbps, HDCP & EDID Management, Control : TCP/IP and RS-232, Cable Link Monitoring: Integrated HDBaseT link status monitoring | No. | 1 | 225000 | 45000 | 180000 | 3600 | 183600 | 7344 | 190944 | 40613.7888 | 231557.7888 | 34733.6683 | 266291.4571 | 266291
4 | Supply, Installation, Testing & Commessioning of HDBaseT receiver for HDMI with USB System Type: HDBaseT Receiver for HDMI with USB,Input Port: 1 x HDBT, Output Port: 1 x HDMI, Data Port: 2 x USB Hub or more, Signal & Control Extension: Receiver for HDMI, Ethernet, power, control, and USB upto 100mtr using CATxx cable Resolution Support: 4K 60 4:4:4"USB : Signal - 2.0 or better Maximum Data Rate - 480Mbps, Remote powering over HDBaseT or local powering,Chroma Subsampling: 4:4:4,Color Depth: 8-bit, 10-bit, 12-bit, "Audio Support: Pass-through: Dolby Digital Plus, Dolby TrueHD, DTS-HD, Master Audio, DTS:X, HDCP 2.2 & CEC Pass-through Cable Link Monitoring: Integrated HDBaseT link status monitoring | No | 1 | 225000 | 45000 | 180000 | 3600 | 183600 | 7344 | 190944 | 40613.7888 | 231557.7888 | 34733.6683 | 266291.4571 | 266291
5 | Supply, Installation, Testing & Commessioning of 5x2 Universal switcher with built-in / external Wireless Presentation Capable for Soft VC Facility 5 x 2 Multiformat Universal Matrix Switcher with built-in / External Wireless Facility Input Ports: 2 x HDMI, 1 x USB-C, 1 x Mini Display Port Output Ports: Matrix Video Output on HDMI, HDBT 4K 60 4:4:4 ,Automatic input selection using hot plug detect and video detection technology, EDID Management, HDCP Management (HDCP 2.2 Compliant), CEC Enable, Multi Channel Audio Compliant PCM, Dolby Digital, DTS Digital Surround etc Integrated HDBaseT link status monitoring, Soft VC Ready module with USB Host and USB Hub Ports, USB 2.0 interfacing and extension over HDBaseT,Selectable 4K60 4:4:4 video scaler downscaling Built-in / External Wi-Fi connectivity for an iOS, Android, Mac, Chromebook, or Windows-based device.Shall support Miracast /Chromecast/Air play., Built-in Audio de-embedding, HDBase T Outputs Extends HDMI, Power and Control over a single CAT6a OR CAT7 cable HDMI and HDBT output which can work as mirror mode or individual mode like matrix.HDCP 2.2 and EDID management | No. | 1 | 375000 | 75000 | 300000 | 6000 | 306000 | 12240 | 318240 | 67689.648 | 385929.648 | 57889.4472 | 443819.0952 | 443819
6 | Supply, Installation, Testing & Commessioning of 4 x 4 HDMI Matrix Switcher Input Port: 4 x HDMI, Output Port: 4 x HDMI, Resolution Support : 4K 60 4:4:4 ,Support HDR10 and Dolby® Vision™ @ 60Hz Manual Control: Front Panel Input Selection, LED Indicator: To provide power and input selection status information, Chroma Subsampling: 4:4:4, 4:2:2, 4:2:0, Color Depth 8-bit, 10-bit, 12-bit Audio Support:HDMI IN/Out: DTS 5.1, Dolby Digital+, Dolby TrueHD, DTS-HD Master Audio, Signal Bandwidth: 18 Gbps, HDCP 2.2 compliant, HDCP Management, EDID Management Additional Feature: Independent CEC display control to each output Control: TCP/IP, Configuration: GUI-based configuration using integrated web server HDMI audio extractor and downmix 2channel. | No. | 1 | 325000 | 65000 | 260000 | 5200 | 265200 | 10608 | 275808 | 58664.3616 | 334472.3616 | 50170.8542 | 384643.2158 | 384643
7 | Supply, Installation, Testing & Commessioning of 4K/UHD HDMI Extender Kit with Control and Remote Power : Supports resolutions up to 4K/UHD 60 Hz 4:2:0 System Type: 4K/UHD HDMI Extender Kit with Control and Remote Power Transmitter : Input Port: 1 x HDMI & Output Port : 1 x HDBT Receiver : Input Port: 1 x HDBaseT & Output Port : 1 x HDMI Signal & Control Extension: Tranmitter for AV, Power & Control upto 70mtr using CAT6a/7 cable Resolution Support: 4K/UHD @ 60 Hz with 4:2:0" Remote power, transmitter powers receiver over HDBaseT LED Indicator: To provide power and link status information HDBaseT link test verifies cable, termination, and link qualityChroma Subsampling: 4:4:4, 4:2:2, 4:2:0 Color Depth: 8-bit, 10-bit, 12-bit"Audio Support: HDMI In / HDBaseT Out: LPCM 5.1, LPCM 7.1, Dolby Digital, DTS 5.1, Dolby Digital+, Dolby TrueHD, DTS-HD Master Audio HDCP 1.4/2.2 HDCP 2.2 compliant and supports EDID filtering Bidirectional extension of both RS-232 and IR control commands | No. | 1 | 295000 | 59000 | 236000 | 4720 | 240720 | 9628.8 | 250348.8 | 53249.1898 | 303597.9898 | 45539.6985 | 349137.6882 | 349138
8 | Supply, Installation, Testing & Commessioning of HDMI to USB Video capture with HDMI bypass HDMI input and output with 4K@60Hz support, DVI 1.0 compatible HDCP 2.2 and HDCP 1.x compliant Automatically scales 4K sources to 1080p for USB capture Unit may be powered directly via USB 3.0 Supports video timing stabilization to help ensure a reliable and stable USB capture stream Capturing over USB 3.0 allows uncompressed video and audio data capture (up to 1080p, LPCM 2.0) Supports capturing 2 channel digital audio from either HDMI (LPCM 2.0) or the 3.5mm analog audio input (selectable via configuration software) Compliance with the UAC (USB Audio Class) and UVC (USB Video Class) standards, allows the unit to support most common capture and video streaming software Inputs : 1x HDMI, 1x 3.5mm , Output : 1x HDMI, 1x USB Type-B | No. | 1 | 175000 | 35000 | 140000 | 2800 | 142800 | 5712 | 148512 | 31588.5024 | 180100.5024 | 27015.0754 | 207115.5778 | 207116
9 | Supply, Installation, Testing & Commessioning of secure, high performance control processor, Having ethernet port of 100/1000 Mbps, auto switching, auto negotiating, auto discovery, full/half duplex, industry-standard TCP/IP stack, DHCP, SSL, TLS, IEEE 802.1xX, SNMP, HTTPS. Having minimum Memory SDRAM 1 GB, Flash 8 GB, and External Storage Support, Minimum Control ports of 7no's RELAY OUTPUT, Min 7 no’s I/O port., 1 x Bidirectional RS-232/422/485 port, Minimum 2 x Bidirectional RS-232 ports, Should have BACnet™ for integration (internal or by additional hardware) with existing building management systems like Centralized HVAC, security fire, Should be able to control the complete programmed system, from the IT laptop or PC, comply to CE, UL, FCC. | No. | 1 | 225000 | 45000 | 180000 | 3600 | 183600 | 7344 | 190944 | 40613.7888 | 231557.7888 | 34733.6683 | 266291.4571 | 266291
10 | Supply , Installation , Testing & Commissioning of Touch Control tabletop panel of minimum 10" , capacitive widescreen active‑matrix color display , 1024 x 600 display resolution , Minimum 5 backlit soft‑touch buttons , PoE (Power over Ethernet) , built‑in light sensor , compatible with control processor and complete as per the specifications. | No. | 1 | 165000 | 33000 | 132000 | 2640 | 134640 | 5385.6 | 140025.6 | 29783.4451 | 169809.0451 | 25471.3568 | 195280.4019 | 195280
11 | Supply , Installation , Testing & Commissioning of PTZ Camera with 2K Resolution with 1/2.8 inch or higher high quality CMOS sensor , 2592 x 1944@3FPS super high quality video ,10 x or more zoom with 10x or more digital zoom, Pan Range: 340deg or more With USB2.0, 5 or more preset position and complete as per the specifications. | Nos. | 4 | 95000 | 19000 | 76000 | 1520 | 77520 | 3100.8 | 80620.8 | 17148.0442 | 97768.8442 | 14665.3266 | 112434.1708 | 112434
12 | Supply , Installation , Testing & Commissioning of HDMI Interface Cable with High-speed, 24k gold-plated 19-pin Type A connectors High-flex CL3-rated jacket Supports 4K60 4:4:4 video, 18 Gbps , , Supports 4K60 4:2:0 and 4K30 4:4:4 video , RoHS compliant, Length 1.8 meter complete as per the technical specifications . | Nos. | 18 | 1850 | 370 | 1480 | 29.6 | 1509.6 | 60.384 | 1569.984 | 333.9356 | 1903.9196 | 285.5879 | 2189.5075 | 2190
13 | Supply and Laying of Shielded Twisted Pair Cable , Conductor Metal: Solid Bare Copper with 23 AWG Color Code: Blue/ Grey ( or any combination) , Jacket Material: PVC UL94V-0 and complete as per the specifications. | Mtrs. | 800 | 125 | 25 | 100 | 2 | 102 | 4.08 | 106.08 | 22.5632 | 128.6432 | 19.2965 | 147.9397 | 148
14 | Supply , Installation , Testing & Commissioning of Equipment Rack of Size 32 u , 600 mm (W) , 800 mm (D) with front door , Front door lockable with tinted glass / Fiber sheet , Rear door lockable , Top cover with cable entry provision , Fully vented with blowers , Castors with foot operated brakes , 19″ mounting angles at front and rear , 10 x 16amp sockets and complete as per the specifications. | No. | 1 | 45000 | 9000 | 36000 | 720 | 36720 | 1468.8 | 38188.8 | 8122.7578 | 46311.5578 | 6946.7337 | 53258.2914 | 53258
| Sound System |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Supply , Installation , Testing & Commissioning of MAIN LCR Line Source Speaker:- Line Array Speaker LF - 700W RMS (8 ohms) HF - 110W Continuous RMS(16 ohms,) or above, LF Custom made 2 x 10” driver ferrite magnet, 2.5” in/out Voice coil + 1.5" exit HF or better, Frequency Response 50Hz-18khz, Average Sensitivity - 99dB/W/m LF, 109dB/W/m HF or better, Max SPL 136db peak or above, Nominal Directivity - 100° x 15° , Cabinet - CNC made with tongue & grove assembly 15 and 18mm Baltic birch plywood and complete as per the specifications. | Nos. | 12 | 185000 | 37000 | 148000 | 2960 | 150960 | 6038.4 | 156998.4 | 33393.5597 | 190391.9597 | 28558.794 | 218950.7536 | 218951
16 | Supply , Installation , Testing & Commissioning of Array Frame:- Compact crossbow flying frame for IWAC210,integrated rigging, up to 2.5T load and complete as per the specifications. | Nos. | 3 | 95000 | 19000 | 76000 | 1520 | 77520 | 3100.8 | 80620.8 | 17148.0442 | 97768.8442 | 14665.3266 | 112434.1708 | 112434
17 | Supply , Installation , Testing & Commissioning of Subwoofer:- Subwoofer System with minimum 2 x 18” (4” VC), or above , Frequency Response 34Hz-1500hz or better, Max SPL not less than 140db / 1m, with continuous RMS power of 2600 Watt RMS with programmed power of 5200Watt RMS & peak power of 10400 Watt RMS, with sensitivity of 100 dB, or Better, Nominal Impedance : 4ohms, in birch plywood paint finish etc. and complete as per the specifications. | Nos. | 2 | 147500 | 29500 | 118000 | 2360 | 120360 | 4814.4 | 125174.4 | 26624.5949 | 151798.9949 | 22769.8492 | 174568.8441 | 174569
18 | Supply , Installation , Testing & Commissioning of Stage Monitor:- 2-way loudspeaker System with minimum 1 x 15” (3” VC), or above LF, HF - 1" exit Frequency Response 48Hz-22khz, or better, Max SPL not less than 133db / 1m, with continuous RMS power of 500 - 600 Watt RMS with programmed power of 1000– 1200Watt RMS & peak power of 2000 - 2400 Watt RMS, with sensitivity of 98 dB, or Better, Nominal Impedance : 8 ohms, nominal dispersion : 80 x 50 or better, in birch plywood paint finish etc. and complete as per the specifications. | Nos. | 4 | 65000 | 13000 | 52000 | 1040 | 53040 | 2121.6 | 55161.6 | 11732.8723 | 66894.4723 | 10034.1708 | 76928.6432 | 76929
19 | Supply , Installation , Testing & Commissioning of Front Fill Speaker:- 2-way full range, 120W RMS, 12 ohms, LF Custom made 1 x 6” or above Coaxial driver ferrite magnet, 1.5” in/out Voice coil + 0.75" exit HF, Frequency Response 65Hz-22khz, or better, Average Sensitivity - 90dB/W/m or better, Max SPL 117db peak or better ,Nominal Directivity - 85° conical or better),in birch plywood paint finish with wall mount bracket etc. and complete as per the specifications. | Nos. | 4 | 28500 | 5700 | 22800 | 456 | 23256 | 930.24 | 24186.24 | 5144.4132 | 29330.6532 | 4399.598 | 33730.2512 | 33730
20 | Supply , Installation , Testing & Commissioning of Surround Speaker:- 2-way loudspeaker System with minimum 1 x 8” (2” VC), or above LF, HF - 1" exit Frequency Response 52Hz-22khz, or better, Max SPL not less than 121db / 1m, with continuous RMS power of 200 - Watt RMS with programmed power of 400Watt RMS & peak power of 800 Watt RMS, with sensitivity of 92 dB, or Better Nominal Impedance : 8 /12 ohms, nominal dispersion : 80 conical or better, in birch plywood paint finish with wall mount bracket etc. and complete as per the specifications. | Nos. | 12 | 32500 | 6500 | 26000 | 520 | 26520 | 1060.8 | 27580.8 | 5866.4362 | 33447.2362 | 5017.0854 | 38464.3216 | 38464
21 | Supply , Installation , Testing & Commissioning of Green Room / Control Room Speaker:- 2-way full range, 120W RMS, 12 ohms, LF Custom made 1 x 6” or above Coaxial driver ferrite magnet, 1.5” in/out Voice coil + 0.75" exit HF, Frequency Response 65Hz-22khz, or better, Average Sensitivity - 90dB/W/m or better, Max SPL 117db peak or better ,Nominal Directivity - 85° conical or better),in birch plywood paint finish with wall mount bracket etc. and complete as per the specifications. | Nos. | 2 | 27500 | 5500 | 22000 | 440 | 22440 | 897.6 | 23337.6 | 4963.9075 | 28301.5075 | 4245.2261 | 32546.7336 | 32547
22 | Supply , Installation , Testing & Commissioning of Amplifier for Line Array and Subwoofer:- Professional Four channel Power amplifier, 4 x 800W @ 8 ohms or above, 4 x 1300W @ 4 ohms or above, Sensitivity - 2.03v or better, Frequency Response: 20- 25000Hz, Input Impedance - 20K, Crosstalk - >75dB or better, S/ N ratio 112dB or better, Damping Factor - 800 or better, THD - < 0.05% , Slew Rate - 60V / us or better and complete as per the specifications. | Nos. | 4 | 245000 | 49000 | 196000 | 3920 | 199920 | 7996.8 | 207916.8 | 44223.9034 | 252140.7034 | 37821.1055 | 289961.8089 | 289962
23 | Supply , Installation , Testing & Commissioning of Amplifier for Stage Monitor :- Professional Four channel Power amplifier, 4 x 750W @ 8 ohms or above, 4 x 1100W @ 4 ohms or above, Sensitivity - 1.6v or better, Frequency Response: 10- 25000Hz, Input Impedance - 20K, Crosstalk - >70dB or better, S/ N ratio - > 110dB or better, Damping Factor - 500 or better, THD - < 0.05% , Slew Rate - 30V / us or better and complete as per the specifications. | No. | 1 | 135000 | 27000 | 108000 | 2160 | 110160 | 4406.4 | 114566.4 | 24368.2733 | 138934.6733 | 20840.201 | 159774.8743 | 159775
24 | Supply , Installation , Testing & Commissioning of Amplifier for Surround , Front Fill and Green / Control Room Speaker:- Professional Dual channel Power amplifier, 2x 400W @ 8 ohms or above, 2 x 600W @ 4 ohms or above, Sensitivity - 0.775v ,Frequency Response: 20- 20000Hz , Input Impedance - 20K, Crosstalk - >65dB, S/ N ratio - > 110dB or better, Damping Factor - 350 or better, THD - < 0.1% , Slew Rate - 15V / us or better and complete as per the specifications. | Nos. | 6 | 48500 | 9700 | 38800 | 776 | 39576 | 1583.04 | 41159.04 | 8754.5278 | 49913.5678 | 7487.0352 | 57400.603 | 57401
25 | Supply , Installation , Testing & Commissioning of AV Receiver:- Supply, installation, testing & commissioning of 11.2 Channel Full 4K Ultra HD Network AV Surround Processor with, Dolby Atmos and DTS: x (up to 7.1.4) and auro-3d > immersive 3D sound with effects from overhea,11.2-channel balanced XLR outputs include outputs for 2 powered subwoofers and complete as per the specifications. | No. | 1 | 175000 | 35000 | 140000 | 2800 | 142800 | 5712 | 148512 | 31588.5024 | 180100.5024 | 27015.0754 | 207115.5778 | 207116
26 | Supply , Installation , Testing & Commissioning of Mixer:- 32 total inputs mixing console with Effects, Mid-sweep 3-band mono channel EQ, 4-band stereo channel EQ, 4 buses for flexible signal routing: main stereo bus, four group buses, six auxiliary buses, and send buses for the two internal effect processors etc. and complete as per the specifications. | No. | 1 | 145000 | 29000 | 116000 | 2320 | 118320 | 4732.8 | 123052.8 | 26173.3306 | 149226.1306 | 22383.9196 | 171610.0501 | 171610
27 | Supply , Installation , Testing & Commissioning of Digital Controller:- 4 in x 8 Out Networkable Loudspeaker Management System, High precision 32-bit floating point TEXAS INSTRUMENT DSP (48kHz sampling rate)24-bit D/A converters with 118B dynamic range and audiophile grade preamps, On each output: Routing, Delay, Gain, HPF and LPF filters (up to 48dB/oct), 8 filters (PEQ and Shelving), Compressor / Limiter (Threshold, Attack, Release, Ratio) and complete as per the specifications. | No. | 1 | 165000 | 33000 | 132000 | 2640 | 134640 | 5385.6 | 140025.6 | 29783.4451 | 169809.0451 | 25471.3568 | 195280.4019 | 195280
28 | Supply , Installation , Testing & Commissioning of Gooseneck Microphone:- 16.5" Gooseneck cardioid Microphone, polar pattern cardioid, Frequency Range 70-16000 Hz, Sensitivity14.1mV/Pa, Dynamic Range >106dB. Complete with mic base unit etc. and complete as per the specifications. | Nos. | 2 | 19500 | 3900 | 15600 | 312 | 15912 | 636.48 | 16548.48 | 3519.8617 | 20068.3417 | 3010.2513 | 23078.593 | 23079
29 | Supply , Installation , Testing & Commissioning of Wireless Handheld Microphone:- Wireless Handheld Microphone with transmitter and rack mountable Receiver, UHF frequency range, selectable Operating Frequencies , 500 - 865 MHz, 100dB A- weighted, Audio Bandwidth 35 Hz to 20 kHz (+/- 2dB). True Diversity antenna compatible, Complete with adapter batteries and rack mount kit for the receiver, 30 mW min RF radiation etc. and complete as per the specifications. | Nos. | 2 | 37500 | 7500 | 30000 | 600 | 30600 | 1224 | 31824 | 6768.9648 | 38592.9648 | 5788.9447 | 44381.9095 | 44382
30 | Supply , Installation , Testing & Commissioning of Wireless Lapel Microphone:- Wireless Lapel Microphone with transmitter and rack mountable Receiver, UHF frequency range, selectable Operating Frequencies , 500 - 865 MHz, 100dB A- weighted, Audio Bandwidth 35 Hz to 20 kHz (+/- 2dB). True Diversity antenna compatible, Complete with adapter batteries and rack mount kit for the receiver, 30 mW min RF radiation etc. and complete as per the specifications. | Nos. | 2 | 37500 | 7500 | 30000 | 600 | 30600 | 1224 | 31824 | 6768.9648 | 38592.9648 | 5788.9447 | 44381.9095 | 44382
31 | Supply , Installation , Testing & Commissioning of Wired Vocal Microphone:- Vocal Microphone, polar pattern Super cardioid, Frequency Response 80–12,000 Hz Open Circuit Sensitivity –53 dB (2.2 mV) re 1V at 1 Pa* Impedance 600 ohms Switch MagnaLock™ ON/OFF and complete as per the specifications. | Nos. | 4 | 12500 | 2500 | 10000 | 200 | 10200 | 408 | 10608 | 2256.3216 | 12864.3216 | 1929.6482 | 14793.9698 | 14794
32 | Supply , Installation , Testing & Commissioning of Wired Instrument Microphone:- Dynamic Instrumental Microphone, Frequency Response 60–14,000 Hz, Open Circuit Sensitivity –54 dB (1.9 mV) re 1V at 1 Pa* Impedance 600 ohms Switch MagnaLock™ ON/OFF and complete as per the specifications. | Nos. | 4 | 12500 | 2500 | 10000 | 200 | 10200 | 408 | 10608 | 2256.3216 | 12864.3216 | 1929.6482 | 14793.9698 | 14794
33 | Supply and Laying of Microphone Cable:- Laying & Fixing of of Microphone lines high grade, professional low-noise, 2 core high conductivity PVC insulated in PVC jacket, shielded copper cable with Di- electric insulator both end with XLR m/f connector and complete as per the specifications. | Mtrs. | 2600 | 125 | 25 | 100 | 2 | 102 | 4.08 | 106.08 | 22.5632 | 128.6432 | 19.2965 | 147.9397 | 148
34 | Supply and Laying of Speaker Cable:- Laying & Fixing of speaker lines: 4 core, 1.5 sq. mm high definition speaker cable, PVC insulated in PVC jacket laid in existing conduits and complete as per the specifications. | Mtrs. | 300 | 110 | 22 | 88 | 1.76 | 89.76 | 3.5904 | 93.3504 | 19.8556 | 113.206 | 16.9809 | 130.1869 | 130
35 | Supply and Laying of Speaker Cable:- Laying & Fixing of speaker b lines: 2 core, 2.5 sq. mm high definition speaker cable, PVC insulated in PVC jacket laid in existing conduits and complete as per the specifications. | Mtrs. | 1500 | 145 | 29 | 116 | 2.32 | 118.32 | 4.7328 | 123.0528 | 26.1733 | 149.2261 | 22.3839 | 171.6101 | 172
36 | Supply , Installation , Testing & Commissioning of Floor Junction Box:- floor junction boxes on the stage for the various mic inputs with xlr inputs on the boxes and complete as per the specifications. | Nos. | 8 | 6500 | 1300 | 5200 | 104 | 5304 | 212.16 | 5516.16 | 1173.2872 | 6689.4472 | 1003.4171 | 7692.8643 | 7693
37 | Supply , Installation , Testing & Commissioning of Floor Microphone Stand:- Floor Standing Microphone Stand etc. and complete as per the specifications. | Nos. | 4 | 2850 | 570 | 2280 | 45.6 | 2325.6 | 93.024 | 2418.624 | 514.4413 | 2933.0653 | 439.9598 | 3373.0251 | 3373
38 | Supply , Installation , Testing & Commissioning of Table Top Microphone Stand:- Table Top Microphone Stand etc. and complete as per the specifications. | Nos. | 4 | 1450 | 290 | 1160 | 23.2 | 1183.2 | 47.328 | 1230.528 | 261.7333 | 1492.2613 | 223.8392 | 1716.1005 | 1716
| Stage Lighting |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Supply , Installation , Testing & Commissioning of 200W Full Power light Source, Warm Cold: 3200K and Cold White: 5600K.6 meters effective range,10000 hours lifespan. 2/4 Channels [4 Control Mode] Automatic/ Rapid Response Sound Active/ Master-Slave Mode / DMX-512 remote controller [Features] Y axis 180 degrees and stable mounting brackets ensure the light can be wall hanging or up lighting. [Occasion] Professional Stage lighting kits, Super bright for Stage show, Home Party, Street live, Cinema, photography , IP 20 protection and complete as per the specifications. | Nos. | 10 | 17500 | 3500 | 14000 | 280 | 14280 | 571.2 | 14851.2 | 3158.8502 | 18010.0502 | 2701.5075 | 20711.5578 | 20712
40 | Supply , Installation , Testing & Commissioning of 200watt Plano Convex Spot Light with Having CRI TLCI Values above 95 High precision steady color ,No heat, DmX 512 dimming with 2 Channel Beam Angle 15°/ 25° / 45°, 0 ~ 100%, Powder coated Black finish housing Rigidly built pressure die-casted Aluminum body LED Easy view display Flicker Free for high FPS Smooth fade in and Fade out Data DmX through 3 / 5 Pin XLR’s Total Power Consumption of 200W IP20 protection and complete as per the specifications. | Nos. | 6 | 45000 | 9000 | 36000 | 720 | 36720 | 1468.8 | 38188.8 | 8122.7578 | 46311.5578 | 6946.7337 | 53258.2914 | 53258
41 | Supply , Installation , Testing & Commissioning of LED Fresnel Light with VOLTAGES: 100~240V AC，50/60Hz, POWER CONSUMPTION: 179.6W @ 220V, LIGHT SOURCE: Citizen 200W LED, COLOR TEMPERATURE: 3000K, LUMENS: 2982lm~5845lm, BEAM ANGLE: 30°~87°, DIMMER: 1~100% linearly adjustable, CONTROL: DMX512, 5 pin interfaces , 1 channel in standard mode, WORK ENVIRONMENT TEMPERATURE: -20°C~40°C, HOUSING: High-intensity extruding aluminum, IP20, WEIGHT: 6kg, OTHER FUNCTIONS: Low noise(<30dB), CRI:83, Lumens for high light 6000lm, Ideal for television studios, theatres, various conference rooms, multifunctional halls and other locations as functional lighting and complete as per the specifications. | Nos. | 6 | 48750 | 9750 | 39000 | 780 | 39780 | 1591.2 | 41371.2 | 8799.6542 | 50170.8542 | 7525.6281 | 57696.4824 | 57696
42 | Supply , Installation , Testing & Commissioning of 24 x 3W/ 36x3W LED Long BAR Light with Electrical: Voltage: AC100~240V... 50/60Hz, Rated Power: 72W, LED: 24* RGB X 3 W, Beam Angle: 40°. Functions: RGBW color mixing / Custom programs / Strobe / white Balance / RGB and complete as per the specifications. | Nos. | 6 | 39250 | 7850 | 31400 | 628 | 32028 | 1281.12 | 33309.12 | 7084.8498 | 40393.9698 | 6059.0955 | 46453.0653 | 46453
43 | Supply , Installation , Testing & Commissioning of 200 watt LED Profile Spot with Lamp power: 200 watt, Power Supply 110v-220V 50Hz, Beam Angle 19 Degree, Control: DMX Auto rum and master/Slave,CRI:>90,Colour Temperature: 3200K, Shutter: Beam Shaping shutter or plasticgobo projection assembly, IP Rate:20 and complete as per the specifications. | Nos. | 6 | 43500 | 8700 | 34800 | 696 | 35496 | 1419.84 | 36915.84 | 7851.9992 | 44767.8392 | 6715.1759 | 51483.015 | 51483
44 | Supply , Installation , Testing & Commissioning of 100 W Full Power light Source, Warm Cold: 3200K and Cold White: 5600K.6 meters effective range,10000 hours lifespan. 2/4 Channels [4 Control Mode] Automatic/ Rapid Response Sound Active/ Master-Slave Mode / DMX-512 remote controller [Features] Y axis 180 degrees and stable mounting brackets ensure the light can be wall hanging or up lighting. [Occasion] Professional Stage lighting kits, Super bright for Stage show, Home Party, Street live, Cinema, photography , IP 20 protection and complete as per the specifications. | Nos. | 8 | 15750 | 3150 | 12600 | 252 | 12852 | 514.08 | 13366.08 | 2842.9652 | 16209.0452 | 2431.3568 | 18640.402 | 18640
45 | Supply , Installation , Testing & Commissioning of LED PAR Light with 54 x 3W high quality LED’s , 100-120V and 200- 240V AC, 50/60Hz (210W@220V), RGBW color mixing +3200K ~ 10000K linearly adjustable color temperature, 0- 100% linearly adjustable dimmer, Strobe 0~20 F.P.S, Beam Angle: 45°, LED board temperature display, DMX mode, display setting status, operation mode can be transmitted by synchronous control, Standard, Type:LED-354RGB and complete as per the specifications. | Nos. | 14 | 19500 | 3900 | 15600 | 312 | 15912 | 636.48 | 16548.48 | 3519.8617 | 20068.3417 | 3010.2513 | 23078.593 | 23079
46 | Supply , Installation , Testing & Commissioning of Moving Head Wash 30W * 19 LEDs (RGBW 4-in-1), Zoom range 3° - 50° , Individual control of LED rings Small, compact and light weight Linear CTO from 3200K - 7200K, Light source: 30W (RGBW 4-in-1) 19 LEDs (White/Amber LED optional), Expected average lifetime: 50000 hours, Beam angle: Zoom range 3° - 50°, Photometric Total Output (Lumen): 4830 lumens narrow/6450 lumens wide and complete as per the specifications. | Nos. | 4 | 85000 | 17000 | 68000 | 1360 | 69360 | 2774.4 | 72134.4 | 15342.9869 | 87477.3869 | 13121.608 | 100598.9949 | 100599
47 | Supply , Installation , Testing & Commissioning of 300W Beam, Spot, Wash (3 in 1) Moving Head with Input Voltage: AC90/240C, 50-80Hz, Lamp: 15R 300W (OSRAM), Power: 500W, Life Time: 2200 hrs., DMX Channels: 16CH / 24CH / 30CH, Pan: 540° (16bit), Tilt: 245° (16bit), Color Wheel: 13 dichroic filters + white, Rotating Gobo Wheel: 9 Bidirectional and index able gobos, Static Gobo Wheel: 14 fixed gobos at variable rotation, Strobe: 0-13f/s, random or pulse flash, speed adjustable strobe macro function, Dimmer: 0-100% linear light dimming and complete as per the specifications. | Nos. | 4 | 135000 | 27000 | 108000 | 2160 | 110160 | 4406.4 | 114566.4 | 24368.2733 | 138934.6733 | 20840.201 | 159774.8743 | 159775
48 | Supply , Installation , Testing & Commissioning of 3000W Smoke Machine with Power: AC230V/Ac240V, 50Hz-60Hz, Heater: 3000W, Output: 40,000 cu.ft/min., First Heat-up Time: 12 min., Tank Capacity: 6 Liter, Fluid Consumption Rate: 5 min./liter (100% Output), DMX: On Board, Remote operated, Ideal for very large venues, outdoor event, movie production or for fire training concept. Type:S-3000 and complete as per the specifications. | Nos. | 2 | 38500 | 7700 | 30800 | 616 | 31416 | 1256.64 | 32672.64 | 6949.4705 | 39622.1105 | 5943.3166 | 45565.4271 | 45565
49 | Supply , Installation , Testing & Commissioning of Lighting Control Console: with Internal Flash Drive, similar in functionality to a hard disk but faster and more rugged. Provides enough storage for:- The entire Fixture Library of more than 3,000 files, Over a hundred show files, Removable external Memory Stick, Cache the entire Fixture library of more than 3,000 files, Improved method of Fixture selection for Patching, New Locate Fixture button, Fixture Selects (selecting the top row of faders), 2048 Channels, 240 Intelligent Fixtures, 240 Dimmer Control Channels, Theatrical Plotting and Playback functions, Shape Generator for instant creation of patterns and effects, 15 Playback Masters controlling 450 memories, chases or cue lists, MIDI and Bass, Mid, Treble sound to light triggers, Color VGA output fitted as standard and complete as per the specifications. | No. | 1 | 275000 | 55000 | 220000 | 4400 | 224400 | 8976 | 233376 | 49639.0752 | 283015.0752 | 42452.2613 | 325467.3365 | 325467
50 | Supply , Installation , Testing & Commissioning of "J" Clamp made out of MS strip with nut bolt painted in black cloud, Load capacity 60KG and complete as per the specifications. | Nos. | 80 | 350 | 70 | 280 | 5.6 | 285.6 | 11.424 | 297.024 | 63.177 | 360.201 | 54.0302 | 414.2312 | 414
51 | Supply , Installation , Testing & Commissioning of Light Point Wiring from Distribution Board to be provided near stage to various stage light fixtures with 2.5 Sq. mm 3 Core PVC Insulated and PVC Sheathed Cable including Cable Tray of suitable size for laying these wires on the tray including 20 amps metallic clad sockets/ 15 Amp Socket to direct points with box at top and complete as per the specifications. | Nos. | 30 | 5200 | 1040 | 4160 | 83.2 | 4243.2 | 169.728 | 4412.928 | 938.6298 | 5351.5578 | 802.7337 | 6154.2915 | 6154
52 | Supply , Installation , Testing & Commissioning of DMX 2 No. 26500 53000 Splitter with one DMX input and 6 buffered outputs and 3 pin / 5 pin XLR connectors. Type: SPL-6/2 and complete as per the specifications. | No. | 1 | 14500 | 2900 | 11600 | 232 | 11832 | 473.28 | 12305.28 | 2617.3331 | 14922.6131 | 2238.392 | 17161.005 | 17161
53 | Supply and Laying of 2 core shielded DMX Cable and complete as per the specifications. | Mtrs. | 1000 | 112 | 22.4 | 89.6 | 1.792 | 91.392 | 3.6557 | 95.0477 | 20.2166 | 115.2643 | 17.2896 | 132.554 | 133
54 | Supply , Installation , Testing & Commissioning of Electrical Panel made out of CRC sheet painted in gray color, wall mountable with 32 amp S/P MCB- 40, 63 amp 4 pole MCB, Indicator, bus bar and required accessories and complete as per the specifications. | No. | 1 | 145000 | 29000 | 116000 | 2320 | 118320 | 4732.8 | 123052.8 | 26173.3306 | 149226.1306 | 22383.9196 | 171610.0501 | 171610
| CC TV System |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Supply , Installation , Testing & Commissioning of Supply, Installation, Testing & Commissioning of Outdoor IR IP Bullet Camera with 1/2.8" CMOS sensor, 5MP (2592 x 1944) min individually configured 3 independent streams simultaneously; Min WDR 120 dB; MFZ Lens (Zoom/ focus) 2.8-12mm(, F1.6 ~ F3.0+) ; H.265 HEVC/H.264/MJPEG - Video Compression; Defog, BLC, HLC, 2D/3D DNR; AWB, AGC, ICR; Internal 850nm high efficiency array IR with 60 Meter IR distance, 1/1 Alarm I/O; 10/100 RJ45; Two way full duplex Audio, G.711a / G.711 ; 256GB Memory SD card support with ANR / Back-filling Feature, PoE/PoE; 12VDC, IP66, IK10 rated; Rectangle ROIs - Min 8 with 04 no of privacy masking areas; TLS1.2 stream encryption; Digitally Signed Firmware & Authenticated MAC; Digital Certificate based authentication ; AES256; 802.1X, IP Filter, Digest authentication; PCIDSS or UL -CAP compliance; NDAA compliant on-board processor Having Operating temp range : –20°C to 60° C, 90% RHNC; MTBF Compliance - Telcordia SR-332 or RCM or MIL-HDBK-217 or RCR-9102 standard; Certifications: UL/cUL/ BIS-IS13252, CE/equivalent BIS, FCC / equivalent BIS; (EN 55032 / equivalent BIS; EN 50130-4/equivalent BIS; EN 63000 / equivalent BIS; BIS/IS/IEC 62368:Part1: 2018 or IEC 62368-1:2018; RoHS, ONVIF - G,S,T. Cyber Security Certificate - NIST or NCSC-UK, Secure-By-Deafult or UL-CAP or STQC -ERTL or IS 27032. On-board edge analytics & events - People counting, Video motion detection, Alarm input, Recording notification, Tampering, Loitering,Tripwire, Smart Motion Detection.Camera must be supplied complete with all accessories; mounts; SD Cards; Power Supplies as per site requirement & compliance of enclosed detail technical specification and complete as per the specifications. | Nos. | 15 | 59500 | 11900 | 47600 | 952 | 48552 | 1942.08 | 50494.08 | 10740.0908 | 61234.1708 | 9185.1256 | 70419.2964 | 70419
56 | Supply , Installation , Testing & Commissioning of Supply, Installation, Testing & Commissioning of Indore IR IP Bullet Camera with 1/2.8" CMOS sensor, 5MP (2592 x 1944) min individually configured 3 independent streams simultaneously; Min WDR 120 dB; MFZ Lens (Zoom/ focus) 2.8-12mm(, F1.6 ~ F3.0+) ; H.265 HEVC/H.264/MJPEG - Video Compression; Defog, BLC, HLC, 2D/3D DNR; AWB, AGC, ICR; Internal 850nm high efficiency array IR with 60 Meter IR distance, 1/1 Alarm I/O; 10/100 RJ45; Two way full duplex Audio, G.711a / G.711 ; 256GB Memory SD card support with ANR / Back-filling Feature, PoE/PoE; 12VDC, IP66, IK10 rated; Rectangle ROIs - Min 8 with 04 no of privacy masking areas; TLS1.2 stream encryption; Digitally Signed Firmware & Authenticated MAC; Digital Certificate based authentication ; AES256; 802.1X, IP Filter, Digest authentication; PCIDSS or UL -CAP compliance; NDAA compliant on-board processor Having Operating temp range : –20°C to 60° C, 90% RHNC; MTBF Compliance - Telcordia SR-332 or RCM or MIL-HDBK-217 or RCR-9102 standard; Certifications: UL/cUL/ BIS-IS13252, CE/equivalent BIS, FCC / equivalent BIS; (EN 55032 / equivalent BIS; EN 50130-4/equivalent BIS; EN 63000 / equivalent BIS; BIS/IS/IEC 62368:Part1: 2018 or IEC 62368-1:2018; RoHS, ONVIF - G,S,T. Cyber Security Certificate - NIST or NCSC-UK, Secure-By-Deafult or UL-CAP or STQC -ERTL or IS 27032. On-board edge analytics & events - People counting, Video motion detection, Alarm input, Recording notification, Tampering, Loitering,Tripwire, Smart Motion Detection.Camera must be supplied complete with all accessories; mounts; SD Cards; Power Supplies as per site requirement & compliance of enclosed detail technical specification and complete as per the specifications. | Nos. | 6 | 59500 | 11900 | 47600 | 952 | 48552 | 1942.08 | 50494.08 | 10740.0908 | 61234.1708 | 9185.1256 | 70419.2964 | 70419
57 | Supplying, installation , testing and commissioning of Cyber Security Certified and GFR -GOI(Land Border) & NDAA compliant 16 channel NVR having a minimum ARM processor or better, 02 no of internal HDDs upto 10 TB each support, on-board OS - Linux or Embedded LINUX or MS-OS or MAC, inbuilt I/Os - 8 / 2, 01 no of 10/100/1000Mbps Ethernet (RJ-45) x 1, in-built HDMI x 1 (4K Max) & VGA x1 of 1080P; complying with H.265 HEVC smart codec or better dual codec decoding, 128 MBPs throughput, 8MP /4K Ultra HD (UHD decoding capability for viewing and recording cum play back ; viewing of 1 to 16 channels simultaneously with synchronized real-time playback on monitor ; supports de-warp fisheye camera video; supports for Tampering, Intrusion, Crowd Detection, Multi-Loitering; supports two way audio/push notification for incident management; supports mobile apps in Apple/MAC and Android OS; supports end to end encrypted solution, with video streaming encrypted from cameras to NVR, and video streaming/control encrypted between NVR and web client/viewer/mobile Apps; supports & compliant to PCI-DSS compliance & Global P2P Service; supports exporting user-selected image or video clips through secured encrypeted digital signatures; supports a minimum of 130W PoE power; Operating environment - -10°C ~ 55°C, 90% RHNC; Certifications - EN 55035; BIS; RCM; UL LISTED TO UL/CSA 62368-1; FCC Part 15, CE/ EN 61000-3-2, EN 61000-3-3 | No. | 2 | 165000 | 33000 | 132000 | 2640 | 134640 | 5385.6 | 140025.6 | 29783.4451 | 169809.0451 | 25471.3568 | 195280.4019 | 195280
58 | Supply , Installation , Testing & Commissioning of Cyber Security Certified, ONVIF - G,S,T compliant UNIFIED NVMS Application for a minimum of 32 having with H.265 HEVC or better video compression; N+1 redundancy; with all necessary Licenses; supports secure HTTPS & TLS1.2 Connection; viewing of live and recordings from Maps in HTML5 browsers ; digest authentication; in-built application level protection against CSRF and XSS cyber attacks; GDPR compliant; digtial signing for data export including web & mobile clients; complete map support with/on GIS; Auto-cad; Jpegs & Auto -cad maps; supports & compliant to encrypting of SQL Server communications (Over SSL); encrypted video stream with TLS 1.2, create/edit IP filter lists; IPsec secured communication using AES 256/3DES for Encryption and SHA1/MD5 for Integrity, supports crypto security either TPM 2.0 or FIPS -140-2 or PTT; enable IPSec policy with OS Firewall policy; using HTTPS as the default communication protocol;100 characters mailing ability per mail text/message; video wall integrations for live & recorded video; instant Playback of 16x / 32x both in reverse and forwards; LDAP & SSO; .Cyber Security Certificate -UL CAP or NIST or NCSC Secure by Default or ISO/IEC 27032 or STQC-ERTL. and complete as per the specifications. | No. | 1 | 375000 | 75000 | 300000 | 6000 | 306000 | 12240 | 318240 | 67689.648 | 385929.648 | 57889.4472 | 443819.0952 | 443819
59 | Supply, Installation, Testing, Commissioning of Surveillance 6TB Hard disk surveliance category I/c connection , configration . | No. | 1 | 28000 | 5600 | 22400 | 448 | 22848 | 913.92 | 23761.92 | 5054.1604 | 28816.0804 | 4322.4121 | 33138.4924 | 33138
60 | Supply , Installation , Testing & Commissioning of Access switch having 32 x 10/100/1000Base T ports with 2x SFP+ up link ports with a dedicated stacking port and RPS supported from Day 1.Min Operating temp 0-45 Degree C ,Must have Common criteria certification EAL3/NDcPP/NDPP, Switch should support additional 2*10G SFP ports if required apart from what's been proposed from day 1 .Min 370 Watt PoE/PoE+ power budget based on IEEE 802.3af/IEEE 802.3at.Auto adjustable fan based on temperature variation and complete as per the specifications. | No. | 1 | 175000 | 35000 | 140000 | 2800 | 142800 | 5712 | 148512 | 31588.5024 | 180100.5024 | 27015.0754 | 207115.5778 | 207116
61 | Supply and Laying of CAT 6 UTP cable 23 AWG solid copper conductors with flame retardant properties, in compliance to relevant IEC standards and complete as per the specifications. | Mtrs. | 1000 | 65 | 13 | 52 | 1.04 | 53.04 | 2.1216 | 55.1616 | 11.7329 | 66.8945 | 10.0342 | 76.9286 | 77
62 | Supply , Installation , Testing & Commissioning of 65 inch 4K Android LED display with built in 2.4 Hz Wifi, IPS / VA Panel Technology, Landscape & Orientation Resolution 3840X 2160 (16.9) UHD. Brightness 350 NIT, Built in Wi-Fi and Bluetooth inbuilt digital signage player, Android Built in Memory 16 GB, Processor Cortex A55x4 1.1 Hz Built in Quad core Processor, 2 GB DDR3 RAM, Triple Core Mali 470 600 MHz 16 GB Memory 24/7 operation, Contrast Ratio 1100:1, 178/178 Viewing Angle (Horizontal: Vertical), 600 MHz GPU, HDR 10, Dolby Audio, 8ms Response Time (milli seconds) Built in speaker (10W+10W). Built in Wifi and Comcast, Built in web browser, HDMI CEC, HDMI ARC, Built-in Bluetooth Ver.4, 20W built in speakers, HDMI 2.0 X 3, AV X 1, USB 2.0 X 1, RJ45 X 1, Headphone Out x 1, SPDIF Out x 1,Inputs DVI-D, Display Port, HDMI & Dual USB, Plug & Play , RJ45 LAN, Output Stereo mini Jack, Remote, Controlling of device Display remotely controlled, Internal/External, BIS Certificates etc. and complete as per the specifications. | No. | 1 | 125000 | 25000 | 100000 | 2000 | 102000 | 4080 | 106080 | 22563.216 | 128643.216 | 19296.4824 | 147939.6984 | 147940